## Aggregates
Vermont Agency of Transportation
Municipal Assistance Bureau
Materials Record
Resident Engineer: | [5 empty] | Project:
Project Supervisor:
Item | Pay Item | Material No. / Tests | Contract Quantity | Sample Freq. | Samples Required
Earth Borrow | 203.3 | 203.11(d)
|  | Moisture |  | 1/2000 cy
|  | Density |  | 1/2000 cy
Granular Backfill for Structures | 204.3 | 703.04
|  | Gradation |  | 1/5000 cy
204.08
|  | Moisture |  | 1/500 cy
|  | Density |  | 1/500 cy
Gravel for Subbase | 301.15 | 704.04
|  | Gradation |  | 1/3000 cy
|  | Percent of Wear |  | 1/10,000 cy/source
301.06
|  | Moisture |  | 1/2000 cy
|  | Density |  | 1/2000 cy
Subbase of Crushed Gravel, Fine | 301.26 | 704.05
|  | Gradation |  | 1/3000 cy
|  | Fractured Faces |  | 1/3000 cy
|  | Percent of Wear |  | 1/10,000 cy/source
301.06
|  | Moisture-Density |  | 1/10,000 cy/source
|  | Moisture |  | 1/2000 cy
|  | Density |  | 1/2000 cy

## Aggregates (2)
Vermont Agency of Transportation
Municipal Assistance Bureau
Materials Record
Resident Engineer: | [5 empty] | Project:
Contractor:
Item | Pay Item | Material No. / Tests | Contract Quantity | Sample Freq. | Samples Required
Subbase of Dense Graded Crushed Stone | 301.35 | 704.06
|  | Gradation |  | 1/3000 cy
|  | Thin & Elongated |  | 1/3000 cy
|  | Percent of Wear |  | 1/10,000 cy/source
301.06
|  | Moisture |  | 1/1000 cy
|  | Density |  | 1/1000 cy
Reclaimed Stabilized Base | 310.2 | 310.02
|  | Gradation |  | 1/2500 sy for first 10,000 sy 1/10,000 sy thereafter
|  | Moisture & Density |  | 1/4000 sy for first 10,000 sy 1/10,000 sy thereafter
Paint for Pavement | 646.2 | 708.08d |  | 1 per Batch
Paint for Pavement | 646.21 | 708.08d |  | 1 per Batch
Paint for Pavement | 646.31 | 708.08d |  | 1 per Batch
Paint for Pavement | 646.32 | 708.08d |  | 1 per Batch

## Hot Mix
Vermont Agency of Transportation
Municipal Assistance Bureau
Materials Record
Resident Engineer: | [5 empty] | Project:
Contractor:
Item | Pay Item | Material No. / Tests | Contract Quantity | Sample Freq. | Samples Required
Emulsified Asphalt | 404.46 | 702.04 | 45 CWT | 1/200 CWT | 1
Bituminous Concrete Pavement | 406.25 | 406.03 | 65,400 Tons | 1/500 Tons first then 1/1000 Tons thereafter | 66
% AC, Gradation, Air Voids, VMA & VFA, Mix Temp.
|  | 702.02 |  | 1/1000 Tons of Mix | 66
Unit Weight, Flashpoint DSR's, m-value
|  | 704.1 |  | 1/10,000 Tons | 7
T&E, and F.F.
|  | 406.14 |  | <0.5 Mi, 4/day. ; >0.5 mi. 6/day | 6/ day
Mat Density
*When the contract calls for Air Voids and Mat Density Pay adjustments, testing frequencies Shall be in accordance with section 106.03

## Concrete
Vermont Agency of Transportation
Municipal Assistance Bureau
Materials Record
Resident Engineer: | [5 empty] | Project:
Contractor:
Item | Pay Item | Material No. / Tests | Contract Quantity | Sample Freq. | Samples Required
Strucural Concrete Class A | 541.22 | 541.06 |  | 1/50 CY Super structure, 1/75 CY Substructure
Slump, Air, Temp. Cylinders
|  | 704.01&02 |  | 1/400 CY
Gradation
|  | 701.02 |  | 1/ day Decks only
cubes
Strucural Concrete Class B | 541.25 | 541.06 |  | 1/50 CY Super structure, 1/75 CY Substructure
Slump, Air, Temp. Cylinders
|  | 704.01&02 |  | 1/400 CY
Gradation
|  | 701.02 |  | 1/ day Decks only
cubes
Reinforcing Steel | 507.15 | 713.01 |  | 1/100,000/ size / grade
Epoxy coated Steel | 507.17 | 713.07 |  | 1/100,000/ size / grade
Mechanical Bar Con. | 507.19 | 713.02 |  | 3 per size
structural Steel Bolts | 506.55 | 714.05 |  | 4 - Each of bolt lot, nut lot, and washer lot
Bridge Railing | 625.22 | 714.07 |  | 2 per lot

## MSM Level 1 & 2
Type of Construction | Pay Item Number | Materials Specification Number | Material Name | Test | Minimum Acceptance Sampling Frequency | Acceptance Sampling Location | Sample Size (2) | Sampling | Procedure
Embankments | 203.3 | 703.02 | Earth Borrow | Identification | Visual Classification | Stockpile | 1 | T2 | ASTM D2488
|  |  |  | Moisture-Density | 1/Soil type | Stockpile | 50 | T2 | T99
|  |  |  | Moisture | 1/2000 cy | In place | 2 |  | T255 or T310
|  |  |  | Density | 1/2000 cy | In place |  |  | T191 or T310
| 203.31 | 703.03 | Sand Borrow | Gradation | 1/3000 cy | In place | 22 | T2 | T27 and T11
|  |  |  | Moisture-Density | 1/10,000 cy/source | Stockpile | 50 | T2 | T99
|  |  |  | Moisture | 1/2000 cy | In place | 20 |  | T255 or T310
|  |  |  | Density | 1/2000 cy | In place |  |  | T191 or T310
| 203.32 | 703.04 | Granular Borrow | Gradation | 1/3000 cy | In place | 22 | T2 | T27 and T11
|  |  |  | Moisture-Density | 1/10,000 cy/source | Stockpile | 50 | T2 | T99
|  |  |  | Moisture | 1/2000 cy | In place | 2 |  | T255 or T310
|  |  |  | Density | 1/2000 cy | In place |  |  | T191 or T310
| 203.35 | 704.07 | Gravel Backfill for Slope Stabilization | Gradation | 1/5000 cy | In place | see note 2 | T2 | T27 and T11
|  |  |  | Moisture-Density | 1/10,000 cy/source | Stockpile | 250 | T2 | T99
|  |  |  | Moisture | 1/5000 cy | In place | 20 |  | T255 or T310
|  |  |  | Density | 1/5000 cy | In place |  |  | T191 or T310
Excavation for Structures | 204.3 | 704.08 | Granular Backfill for Structures | Gradation | 1/3000 cy | In place | see note 2 | T2 | T27 and T11
|  |  |  | Moisture-Density | 1/10,000 cy/source | Stockpile | 250 | T2 | T99
|  |  |  | Moisture | 1/500 cy | In place | 30 |  | T255 or T310
|  |  |  | Density | 1/500 cy | In place |  |  | T191 or T310
Subbase | 301.15 | 704.04 | Gravel for Subbase | Gradation | 1/3000 cy | Stockpile on project | see note 2 | T2 | T27 and T11
|  |  |  | Percent of Wear | 1/10,000 cy/source | Stockpile | 150 | T2 | T96
|  |  |  | Moisture-Density | See Note 8 | Stockpile | 250 | T2 | AOT-MRD 54
|  |  |  | Moisture | 1/2000 cy | In place |  |  | AOT-MRD 55
|  |  |  | Density | 1/2000 cy | In place |  |  | AOT-MRD 55
| 301.25 | 704.05 | Crushed Gravel for Subbase | Gradation | 1/3000 cy | Stockpile on project | see note 2 | T2 | T27 and T11
| 301.26 |  |  | Percent of Wear | 1/10,000 cy/source | Stockpile | 150 | T2 | T96
|  |  |  | Fractured Faces | 1/3000 cy | Stockpile |  | T2 | AOT-MRD 23
|  |  |  | Moisture-Density | See Note 8 | Stockpile | 250 |  | AOT-MRD 54
|  |  |  | Moisture | 1/1000 cy | In place |  |  | AOT-MRD 55
|  |  |  | Density | 1/1000 cy | In place |  |  | AOT-MRD 55
| 301.35 | 704.06 | Dense Graded Crushed Stone for Subbase | Gradation | 1/3000 cy | Stockpile on project | see note 2 | T2 | T27 and T11
|  |  |  | Percent of Wear | 1/source/year | Stockpile | 150 | T2 | T96
|  |  |  | Thin & Elongated Pieces | 1/3000 cy | In place |  | T2 | AOT-MRD 22
|  |  |  | Moisture-Density | See Note 8 | Stockpile | 250 |  | AOT-MRD 54
|  |  |  | Moisture | 1/1000 cy | In place |  |  | AOT-MRD 55
|  |  |  | Density | 1/1000 cy | In place |  |  | AOT-MRD 55
Reclaimed Stabilized Base | 310.2 | 310.02 | Reclaimed Base | Gradation | 1/2500 sy for first 10,000 sy 1/10,000 sy thereafter | In place | 165 | T2 | T27
|  |  |  | Moisture | 1/4000 sy for first 10,000 sy 1/10,000 sy thereafter | In place |  |  | T310
|  |  |  | Density | 1/4000 sy for first 10,000 sy 1/10,000 sy thereafter | In place |  |  | T310
Aggregate Surface Course | 401.1 | 704.12 | Aggregate for Surface Course and Shoulders | Gradation | 1/5000 cy | In place | 100 | T2 | T27 and T11
|  |  |  | Percent of Wear | 1/source/year | Stockpile | 100 | T2 | T96
|  |  |  | Moisture-Density | 1/15,000 cy/source | Stockpile | 100 | T2 | T99
|  |  |  | Moisture | 1/5000 cy | In place |  |  | T255 or T310
|  |  |  | Density | 1/ 5000 cy | In place |  |  | T191 or T310
Aggregate Shoulders | 402.1 | 704.12 | Aggregate for Surface Course and Shoulders | Gradation | 1/5000 cy | In place | 100 | T2 | T27 and T11
| 402.11 |  |  | Percent of Wear | 1/source/year | Stockpile | 100 | T2 | T96
402.12
402.13
Surface Treatments |  |  |  |  | See Specifications
Bituminous Concrete Pavement | 406.25 406.27 | 406.03 | Bituminous Concrete Pavement | AC Content /Gradation | 1/500 tons for first 1,000 tons, 1/1,000 tons thereafter | Truck @ plant | Dependent on mix type - see note 10 | T168 | T164 or T308 & T30
Mainline Paving and Shoulders |  | 406.03 | Medium Duty Bituminous Concrete Pavement | Air voids, VMA & VFA | 1/500 tons for first 1,000 tons, 1/1,000 tons thereafter | Truck @ plant |  |  | T166A, T209, T269, PP19
|  |  |  | Marshall Flow & Stability | 1/500 tons for first 1,000 tons, 1/1,000 tons thereafter | Truck @ plant |  |  | T245
|  |  |  | Mixing Temperature | 1/500 tons for first 1,000 tons, 1/1,000 tons thereafter | Truck @ plant
|  |  |  | Density-mat | Project less than 0.5 miles take 4 cores per day production. Project greater than 0.5 miles 6 cores per day production at the rate of 2 per lane mile | In place | 6" core |  | T166
|  |  |  | Density-joint | See Specifications | In place | 6" core
| 406.25 406.27 | 704.10 | Aggregates for Bituminous Concrete | Percent of Wear | 1/source/year | Stockpile @ plant | Dependent on mix type - see note 9 | T2 | T96
|  |  |  | Thin & Elongated Pieces | 1/10,000 tons/source | Stockpile @ plant |  |  | AOT-MRD22
|  |  |  | Fractured Faces | 1/10,000 tons/source | Stockpile @ plant |  |  | AOT-MRD23
|  |  |  | Soundness | 1/source/year | Stockpile @ plant | 5 | T2 | T104
|  | 702.02 | PG Binder | Unit weight, Flashpoint, Rotational Viscosity, DSR - Original, Effect of heating mass, DSR - RTFO, DSR - PAV, Creep stiffness, m Value | 1/1,000 Tons of Mix | In-line @ plant | 2 Quarts | T40 | T48, T228, T240, T313, T315, T316
|  | 702.04 | Emulsified Asphalt | Distillation, Penetration @ 25 °C | 1/ 200 CWT | Truck on Project | 2 Quarts | T40 | Certification T49, T59
| 490.3 | 490.03 | Superpave Bituminous Concrete Pavement | AC Content / Gradation | 1/500 tons for first 1,000 tons, 1/1,000 tons thereafter | Truck @ plant | Dependent on mix type - see note 10 | T168 | T164 or T308 & T30
|  |  |  | Air voids, VMA & VFA | 1/500 tons for first 1,000 tons, 1/1,000 tons thereafter | Truck @ plant |  |  | T312,T166,T209,T269, R35
|  |  |  | Mixing Temperature | 1/500 tons for first 1,000 tons, 1/1,000 tons thereafter | Truck @ plant
| 490.3 | 490.03 | Superpave Bituminous Concrete Pavement | Density-mat | Project less than 0.5 miles 4 cores per day production. Project greater than 0.5 miles 6 cores per day production at the rate of 2 per lane mile | In place | 6" core | T168 | T166
|  |  |  | Density-joint | See Specifications | In-place | 6" core
|  | 704.10 | Aggregates for Superpave Bituminous Concrete | Percent of Wear | 1/source/year | Stockpile @ plant | Dependent on mix type - see note 9 | T2 | T96
|  |  |  | Thin & Elongated Pieces | 1/10,000 tons/source | Stockpile @ plant |  |  | AOT-MRD22
|  |  |  | Fractured Faces | 1/10,000 tons/source | Stockpile @ plant |  |  | AOT-MRD23
|  |  |  | Soundness | 1/source/year | Stockpile @ plant | 5 | T2 | T104
|  | 702.02 | PG Binder | Unit weight, Flashpoint, Rotational Viscosity, DSR - Original, Effect of heating mass, DSR - RTFO, DSR - PAV, Creep stiffness, m Value | 1/1,000 Tons of Mix | In-line @ plant | 2 Quarts |  | T48, T228, T240, T313, T315, T316
|  | 702.04 | Emulsified Asphalt | Distillation, Penetration @ 25 °C | 1/ 200 CWT | Truck on Project | 2 Quarts | T40 | Certification T49, T59
Non Mainline Paving: Side Roads, Traffic Islands, Gutters, Curbs, Side Walks, Handwork, Drives & Aprons | 406.25 406.27 490.30 | 406.03 | Bituminous Concrete Pavement | AC Content /Gradation | 1/1,000 Tons of Mix | Box Sample on Project | Dependent on mix type - see note 10 | T168 | T164 or T308 & T30
|  | 406.03 | Medium Duty Bituminous Concrete Pavement | AC Content /Gradation | 1/1,000 Tons of Mix | Box Sample on Project |  | T168 | T164 or T308 & T30
|  | 490.3 | Superpave Bituminous Concrete Pavement | Mixing Temperature | 1/1,000 Tons of Mix | Box Sample on Project |  | T168
|  | 702.04 | Emulsified Asphalt | Distillation, Penetration @ 25 °C | 1/Project | Truck on Project | 2 Quarts | T40 | Certification T49, T59
| 616.30 616.31 616.47 | 616.13 | Bituminous Concrete Gutters and Traffic Islands | AC Content / Gradation | 1/1,000 Tons of Mix | Box Sample on Project | Dependent on mix type - see note 10 | T168 | T164 or T308 & T30
|  | 406.03 | Bituminous Concrete Curb Type A | AC Content / Gradation | 1/1,000 Tons of Mix | Box Sample on Project |  | T168 | T164 or T308 & T30
|  | 406.03a | Bituminous Concrete Pavement | AC Content / Gradation | 1/1,000 Tons of Mix | Box Sample on Project |  | T168 | T164 or T308 & T30
|  | 702.04 | Emulsified Asphalt | Distillation, Penetration @ 25 °C | 1/Project | Truck on Project | 2 Quarts | T40 | Certification T49, T59
Structural Concrete | 501.32 501.33 501.34 541.21 541.22 541.25 541.40 580.10 580.11 580.12 580.19 | 501.03 541.03 | HPC Structural Concrete | Air | 1 per 50 cy | on project, as close to point of deposit as possible | 1 ft3 for cylinders or wheelbarrow needed for all tests | T141 | T152
Superstructure |  |  |  | Slump | (See Note 3) |  |  |  | T119
|  |  | Structural Concrete | Temperature |  |  |  | T141 | T309
|  |  |  | Unit weight (light weight) |  |  |  | T141 | T196
|  |  |  | Cylinders |  |  |  | T23 | T22
|  | 704.02A 704.02B 704.14 | Coarse Aggregate for Concrete | Gradation | 1 per 400 cy | at plant | see note 9 | T2 | T27
|  |  |  | Percent of Wear | 1/source/year |  | 11 | T2 | T96
|  |  |  | Fractured Faces | 1 per 1000 cy per source |  | 500 grams | T2 / T248 | AOT-MRD22
|  |  |  | Thin / Elongated Pieces | 1 per 1000 cy per source |  | 500 grams | T2 / T248 | AOT-MRD23
|  |  |  | Soundness | 1/source/year |  | 5 | T2 / T248 | T104
|  |  |  | Density (for lightweight aggregate) | 1 per placement |  | 0.5 to 2 ft3 | T2 | T19
|  | 704.01 | Fine Aggregate for Concrete | Gradation | 1 per 400 cy | at plant | 22 | T2 | T27
|  |  |  | Organic Impurities | 1 per 400 cy |  | 1 | T2 / T248 | T21
|  |  |  | Comp.Strength of Mortar | new source |  | 1 | T2 / T248 | T106
|  |  |  | Soundness | 1/source/year |  | 5 | T2 | T104
|  | 701.02 701.05 701.06 701.07 | Portland and Pozzolan Cements, Blended Silica Fume Cement, Portland Blast Furnace Slag Cement | Compressive Strength - Mortar Cubes, Autoclave Expansion, Normal Consistency, Time of Set - Vicat, Air Content, Fineness - Blaine Apparatus | 1/day (decks only) | at plant | 15 | T127 | Certification T106, T107, T131, T137, T192, ASTM C1437
|  | 725.03(a) 725.03(b) 725.03(c) | Fly Ash, Silica Fume, Ground Granulated Blast Furnace Slag | Compressive Strength - Mortar Cubes, Autoclave Expansion, Time of Set - Vicat, Air Content, Fineness - #325 Sieve | 1/day (decks only) | at plant | 10 | T127 | Certification T106, T107, T131, T137, T192, ASTM C1437
Substructure/Approach Slabs/Retaining Walls/Drilled Shafts/Mast Arm Supports/Overhead Sign Supports | 501.32 501.33 501.34 541.21 541.22 541.25 541.30 541.31 541.40 580.13 580.14 580.15 677.12 677.13 677.22 677.23 678.15 678.17 679.21 679.22 | 501.03 541.03 | HPC Structural Concrete | Air | 1 per 75 cy | on project | 1 ft3 for cylinders or wheelbarrow needed for all tests | T141 | T152
|  |  |  | Slump | (See Note 4) |  |  |  | T119
|  | 541.03 | Structural Concrete | Temperature |  |  |  | T141 | T309
|  |  |  | Unit weight (light weight concrete) |  |  |  | T141 | T196
|  |  |  | Cylinders |  |  |  | T23 | T22
|  | 704.02A 704.02B 704.14 | Coarse Aggregate for Concrete | Gradation | 1 per 400 cy | at plant | see note 9 | T2 | T27
Note: For Mast Arm Supports and Overhead Sign Supports the bolt requirements below may also apply. |  |  |  | Percent of Wear | 1/source/year |  | 11 | T2 | T96
|  |  |  | Fractured Faces | 1 per 1000 cy per source |  | 500 grams | T2 / T248 | AOT-MRD22
|  |  |  | Thin / Elongated Pieces | 1 per 1000 cy per source |  | 500 grams | T2 / T248 | AOT-MRD23
|  |  |  | Soundness | 1/source/year |  | 5 | T2 | T104
|  |  |  | Density (for lightweight aggregate) | 1 per placement |  | 0.5 to 2 ft3 | T2 | T19
|  | 704.01 | Fine Aggregate for Concrete | Gradation | 1 per 400 cy | at plant | 22 | T2 | T27
|  |  |  | Organic Impurities | 1 per 400 cy |  | 1 | T2 / T248 | T21
|  |  |  | Compressive Strength of Mortar | new source |  | 1 | T2 / T248 | T106
|  |  |  | Soundness | 1/source/year |  | 5 | T2 | T104
|  | 701.02 701.05 701.06 701.07 | Cement, Portland Pozzolan Cement, Blended Silica Fume Cement, Portlant Blast Furnace Slag Cement | Compressive Strength - Mortar Cubes, Autoclave Expansion, Normal Consistency, Time of Set - Vicat, Air Content, Fineness - Blaine Apparatus | 1/1000 cy/Type/concrete plant/source | at plant | 15 | T127 | Certification T106, T107, T131, T137, T192, ASTM C1437
|  | 725.03(a) 725.03(b) 725.03(c) | Fly Ash, Silica Fume, Ground Granulated Blast Furnace Slag | Compressive Strength - Mortar Cubes, Autoclave Expansion, Time of Set - Vicat, Air Content, Fineness - #325 Sieve | 1/1000 cy/Type/concrete plant/source | at plant | 10 | T127 | Certification T106, T107, T131, T137, T192, ASTM C1437
Prestress/Precast Concrete/Median Barriers | 510.21 510.22 510.23 540.10 | 510.05 | Concrete | Cylinder strength | per casting bed (note 6) | point of placement | 1 ft3 for cylinders or wheelbarrow needed for all tests | T23 | T22
|  |  |  | Air content | per casting bed (note 7) |  |  | T141 | T152
|  |  |  | Temperature | per casting bed (note 7) |  |  | ASTM C 172 | T309
|  |  |  | Slump (specified on approved mix design) | per casting bed (note 7) |  |  | T141 | T119
|  | 704.01 | Fine Aggregate for Concrete | Gradation | 1 every other day of production | at plant | 22 | T2 | T27
|  |  |  | Organic Impurities | 1 @ beginning of job |  | 1 | T2 / T248 | T21
|  |  |  | Compressive Strength of Mortar | new source |  | 1 | T2 / T248 | T106
|  |  |  | Soundness | new source |  | 5 | T2 | T104
|  | 704.02 | Coarse Aggregate for Concrete | Gradation | 1 every other day of production | at plant | see note 9 | T2 | T27
|  |  |  | Percent of Wear | 1 @ beginning of job |  | 11 | T2 | T96
|  |  |  | Fractured Faces | 1 @ beginning of job |  | 500 grams | T2 / T248 | AOT-MRD22
|  |  |  | Thin / Elongated Pieces | 1 @ beginning of job |  | 500 grams | T2 / T248 | AOT-MRD23
|  |  |  | Soundness | 1/source/year |  | 5 | T2 | T104
|  |  |  | Density (for lightweight aggregate) | 1 per placement |  | 0.5 to 2 ft3 | T2 | T19
|  | 701.02 701.04 701.05 701.06 701.07 | Cement, High Early Portland Cement, Portland Pozzolan Cement, Blended Silica Fume Cement, Portland Blast Furnace Slag Cement | Compressive Strength - Mortar Cubes, Autoclave Expansion, Normal Consistency, Time of Set - Vicat, Air Content, Fineness - Blaine Apparatus | 1 @ beginning of job | at plant | 15 | T127 | Certification T106, T107, T131, T137, T192, ASTM C1437
|  | 725.03(a) 725.03(b) 725.03(c) | Fly Ash, Silica Fume, Ground Granulated Blast Furnace Slag | Compressive Strength - Mortar Cubes, Autoclave Expansion, Time of Set - Vicat, Air Content, Fineness - #325 Sieve | 1/day (decks only) | at plant | 10 | T127 | Certification T106, T107, T131, T137, T192, ASTM C1437
|  |  | Reinforcing Steel |  | See Reinforcing Steel Section
Concrete for Sidewalks/Curbs/Gutters5 | 616.27 616.28 616.45 618.10 618.11 621.45 | 541.03 | Structural Concrete | Air | 1 per 75 cy | on project | 1 ft3 for cylinders or wheelbarrow needed for all tests | T141 | T152
|  |  |  | Slump |  |  |  |  | T119
|  |  |  | Cylinders |  |  |  | T23 | T22
LEVEL 1 PROJECTS ONLY
Structural Steel | 506.50 506.55 506.56 506.57 506.60 506.75 | Project Special Provisions 714.05 714.06 714.12 714.13 | High Strength Bolts for Structural Steel | Rotational Capacity Test Wedge Test | 4 - Each combination of bolt production lot, nut lot, and washer lot (4 - Each combination Tension Control Assembly Bolt production lot or Direct Tension Indicator production lot if used) to be incorporated into the project for main member connections as designated in the Contract. | Original Manufacturer Shipping Container at the project or at fabrication facility | N/A |  | Rotational Capacity Test Specified in AASHTO M 164 M as modified in 714.05 Wedge Test per ASTM F 606
Bridge Railing | 525.22 525.23 525.31 525.33 525.34 525.40 525.41 525.42 | Project Special Provisions 714.07 | Anchor Bolts for Bridge Railing | Wedge Test | 2 - Each combination of anchor bolt production lot, nut lot, and washer lot to be incorporated into the project. | Original Manufacturer Shipping Container at the project or at fabrication facility | N/A |  | Tensile Strength Test ASTM F606 Verification Testing ASTM F606
525.43
525.44
Reinforcing Steel | 507.15 507.17 | 713.01 713.07 | Reinforcing Steel, Epoxy Coated Reinforcing Steel | Tensile testing, elongation | 1/100,000 lb/size/grade | Stockpile on Project | 5 ft |  | AASHTO T244
Mechanical Bar Connectors | 507.19 | 713.02 | Mechanical Splices for Bar Reinforcement | Tensile testing, elongation | 3 per size | Stockpile on Project | connector length plus 12 inches of bar on each end |  | AASHTO T244
Over Head Traffic Sign Supports & Street Lighting | 677.12 677.13 677.22 677.23 677.25 679.xx | Project Special Provisions 714.09 | Anchor Bolts for Sign and Luminaire Poles | Tensile Proof Load Test Elongation Test | 2 - Each combination of anchor bolt production lot, nut lot, and washer lot to be incorporated into the project. | Original Manufacturer Shipping Container at the project or at fabrication facility | N/A |  | Tensile Strength Test ASTM F606 Verification Testing ASTM F606
Note: For Mast Arm Supports and Overhead Sign Supports the concrete requirements above may also apply.
|  |  | High Strength Bolts for Structural Steel | Rotational Capacity Test Wedge Test | 4 - Each combination of bolt production lot, nut lot, and washer lot (4 - Each combination Tension Control Assembly Bolt production lot or Direct Tension Indicator production lot if used) to be incorporated into the project for main member connections as designated in the Contract. | Original Manufacturer Shipping Container at the project or at fabrication facility | N/A |  | Rotational Capacity Test Specified in AASHTO M 164 M as modified in 714.05 Wedge Test per AASHTO M 164M
Paint for Pavement Markings | 646.20 to 646.32 | 708.08 | Waterborne Traffic Paint | Drying time | 1 per batch | Original Container (tote) | 2 - 1 pint containers |  | ASTM D711
|  |  |  | Viscosity |  |  |  |  | ASTM D562
|  |  |  | Density |  |  |  |  | ASTM D1475
Underdrains | 605.10 to 605.23 | 704.16 | Drainage Aggregate | Gradation | 1/3000 cy | On Project | 55 | T2 | T27
|  |  |  | Percent of Wear | 1/source/year |  |  |  | T96
|  |  |  | Soundness | 1/source/year |  | 5 |  | T104
Notes: | (1) Testing procedures are AASHTO procedures unless otherwise noted.
(2) Sample size is in pounds unless otherwise noted. The sample size should be selected based on the maximum nominal aggregate size (See AASHTO T27, Section 7.1). For example, if the material visually passes a 2", 1.5", or 1" sieve then the sample size is 220 lbs, 165 lbs, and 110 lbs, respectively.
(3) Total placement for day split into equal sublots not to exceed 50 CY, test yardage chosen randomly. The test yardage is used to determine which load to test with proper sample collection techniques followed Check first load for temperature, slump and air content, this will not be counted as the acceptance test for the first sublot. If the first load is determined to be out-of-specification then the Contractor must test each consecutive load until 3 consecutive passing loads are tested. VTrans will check 4th consecutive load to verify.
(4) Check first load for temperature, slump and air content as an initial check. Acceptance sampling will be done every 75 CY, including the first load in the yardage count. If the first load, or any acceptance test, does not comply with VTrans' specifications then the Contractor must test each load until 3 consecutive passing loads are achieved. VTrans will check 4th consecutive load or last load, which ever happens first, to verify compliance.
(5) These materials are only required to be tested for Level 1 projects. Those items not identified are considered incidental have no materials testing requirements.
(6) Tests are to be performed by qualified plant personnel and witnessed by VTrans personnel. Minimum of six cylinders for determining detensioning, to be cured with the piece. Four specimens to determine 28 day and shipping strengths and are to be cured with the piece until it is stripped and then standard cured.
(7) Tests are to be performed by qualified plant personnel and witnessed by VTrans personnel. As a minimum, the first load as well as the load that the cylinders are fabricated from should be tested.
(8) For projects less than 1250 CY of subbase material the Agency shall be responsible for the testing and projects over 1250 CY the Contractor is responsible for the determination of the target density. For each material source; subbase materials shall be sampled and tested once for the first 1250 CY and then once every 3000 CY thereafter.
(9) Depends upon the mix type. For mixes with 3/4", 1/2", and 3/8" stone the sample size is 165 lbs, 55 lbs, and 22 lbs respectively.
(10) The sample size for HMA depends upon the nominal maximum aggregate in the mix, see following table. Minimum sample sizes are in accordance with AASHTO T168 and are suitable for routine testing. However, actual sample size is dependent upon the type and number of tests to which the material is to be subjected.
| Mix Type: |  |  | MS | I / IS | II / IIS | III / IIIS | IV / IVS | V / VS
| Maximum Nominal Aggregate Size, in: |  |  | 1 1/2" | 1" | 3/4" | 1/2" | 3/8" | 3/16"
| Minimum Sample Size, lbs: |  |  | 25 | 20 | 16 | 12 | 8 | 4

## MSM Level 3
Type of Construction | Pay Item Number | Materials Specification Number | Material Name | Test | Minimum Acceptance Sampling Frequency | Acceptance Sampling Location | Sample Size (2) | Sampling | Testing (1)
Embankments3 | 203.3 | 703.02 | Earth Borrow | Identification | Visual Classification | Stockpile/in place | 1 |  | ASTM D2488
|  |  |  | Moisture-Density | 1/Soil type | Stockpile/in place | 50 |  | T99
|  |  |  | Moisture | 1/2000 cy | In place | 2 |  | T255 or T310
|  |  |  | Density | 1/2000 cy | In place |  |  | T191 or T310
| 203.31 | 703.03 | Sand Borrow | Gradation | 1 / Project | In place | 22 | T2 | T27 and T11
|  |  |  | Moisture-Density | 1 / Project | Stockpile | 50 | T2 | T99
|  |  |  | Moisture | 1 / Project | In place | 20 |  | T255 or T310
|  |  |  | Density | 1 / Project | In place |  |  | T191 or T310
| 203.32 | 703.04 | Granular Borrow | Gradation | 1 / Project | In place | 22 | T2 | T27 and T11
|  |  |  | Moisture-Density | 1 / Project | Stockpile | 50 | T2 | T99
|  |  |  | Moisture | 1 / Project | In place | 2 |  | T255 or T310
|  |  |  | Density | 1 / Project | In place |  |  | T191 or T310
| 203.35 | 704.07 | Gravel Backfill for Slope Stabilization | Gradation | 1 / Project | In place | see note 2 | T2 | T27 and T11
|  |  |  | Moisture-Density | 1 / Project | Stockpile | 250 | T2 | T99
|  |  |  | Moisture | 1 / Project | In place | 20 |  | T255 or T310
|  |  |  | Density | 1 / Project | In place |  |  | T191 or T310
Excavation for Structures | 204.3 | 704.08 | Granular Backfill for Structures | Gradation | 1 / Project | In place | see note 2 | T2 | T27 and T11
|  |  |  | Moisture-Density | 1/10,000 cy/source | Stockpile/in place | 250 | T2 | T99
|  |  |  | Moisture | 1/500 cy | In place | 30 |  | T255 or T310
|  |  |  | Density | 1/500 cy | In place |  |  | T191 or T310
Subbase3 | 301.15 | 704.04 | Gravel for Subbase | Gradation | 1 / Project | Stockpile on project | see note 2 | T2 | T27 and T11
|  |  |  | Percent of Wear | 1 / Source / Year | Stockpile | 150 | T2 | T96
|  |  |  | Moisture-Density | See Note 10 | Stockpile | 250 | T2 | AOT-MRD 54
|  |  |  | Moisture | 1 / Project | In place |  |  | AOT-MRD 55
|  |  |  | Density | 1 / Project | In place |  |  | AOT-MRD 55
| 301.25 | 704.05 | Crushed Gravel for Subbase | Gradation | 1 / Project | Stockpile on project | see note 2 | T2 | T27 and T11
| 301.26 |  |  | Percent of Wear | 1 / Source / Year | Stockpile | 150 | T2 | T96
|  |  |  | Fractured Faces | 1 / Project | Stockpile |  | T2 | AOT-MRD 23
|  |  |  | Moisture-Density | See Note 10 | Stockpile | 250 |  | AOT-MRD 54
|  |  |  | Moisture | 1 / Project | In place |  |  | AOT-MRD 55
|  |  |  | Density | 1 / Project | In place |  |  | AOT-MRD 55
| 301.35 | 704.06 | Dense Graded Crushed Stone for Subbase | Gradation | 1 / Project | Stockpile on project | see note 2 | T2 | T27 and T11
|  |  |  | Percent of Wear | 1 / Source / Year | Stockpile | 150 | T2 | T96
|  |  |  | Fractured Faces | 1 / Project | Stockpile |  | T2 | AOT-MRD 23
|  |  |  | Moisture-Density | See Note 10 | Stockpile | 250 |  | AOT-MRD 54
|  |  |  | Moisture | 1 / Project | In place |  |  | AOT-MRD 55
|  |  |  | Density | 1 / Project | In place |  |  | AOT-MRD 55
Reclaimed Stabilized Base | 310.2 | 310.02 | Reclaimed Base | Gradation | 1/2500 sy for first 10,000 sy 1/10,000 sy thereafter | In place | 165 | T2 | T27
|  |  |  | Moisture | 1/4000 sy for first 10,000 sy 1/10,000 sy thereafter | In place |  |  | T310
|  |  |  | Density | 1/4000 sy for first 10,000 sy 1/10,000 sy thereafter | in place |  |  | T310
Aggregate Surface Course | 401.1 | 704.12 | Aggregate for Surface Course and Shoulders | Gradation | 1/Project | In place | 100 | T2 | T27 and T11
|  |  |  | Percent of Wear | 1/source/year | Stockpile | 100 | T2 | T96
Aggregate Shoulders | 402.1 | 704.12 | Aggregate for Surface Course and Shoulders | Gradation | 1/Project | In place | 100 | T2 | T27 and T11
| 402.11 |  |  | Percent of Wear | 1/source/year | Stockpile | 100 | T2 | T96
402.12
402.13
Surface Treatments |  |  |  |  | See Specifications
Bituminous Concrete Pavement
Mainline Paving and Shoulders | 406.25 406.27 | 406.03 | Bituminous Concrete Pavement | AC Content /Gradation | 1/1000 tons for first 1,000 tons, 1/day thereafter | Truck @ plant | Dependent on mix type - see note 11 | T168 | T164 or T308 & T30
|  | 406.03 | Medium Duty Bituminous Concrete Pavement | Air voids, VMA & VFA | 1/1000 tons for first 1,000 tons, 1/day thereafter | Truck @ plant |  |  | T166A, T209, T269, PP19
|  |  |  | Marshall Flow & Stability | 1/1000 tons for first 1,000 tons, 1/day thereafter | Truck @ plant |  |  | T245
|  |  |  | Mixing Temperature | 1/1000 tons for first 1,000 tons, 1/day thereafter | Truck @ plant
|  |  |  | Density-mat | Project less than 0.5 miles 4 cores. Project greater than 0.5 miles 6 cores. | In place | 6" core |  | T166
|  |  |  | Density-joint | See Specifications | In place | 6" core |  | T166
|  | 702.04 | Emulsified Asphalt | Distillation, Penetration @ 25 °C | 1/Project | Truck on Project | 2 Quarts | T40 | Certification T49, T59
| 490.3 | 490.03 | Superpave Bituminous Concrete Pavement | AC Content / Gradation | 1/1000 tons for first 1,000 tons, 1/day thereafter | Truck @ plant | Dependent on mix type - see note 11 | T168 | T164 or T308 & T30
|  |  |  | Air voids, VMA & VFA | 1/1000 tons for first 1,000 tons, 1/day thereafter | Truck @ plant |  |  | T312,T166,T209,T269, R35
|  |  |  | Mixing Temperature | 1/1000 tons for first 1,000 tons, 1/day thereafter | Truck @ plant
|  |  | ` | Density-mat | Project less than 0.5 miles 4 cores per day production. Project greater than 0.5 miles 6 cores per day production at the rate of 2 per lane mile | In place | 6" core | T168 | T166
|  |  |  | Density-joint | See Specifications | In place | 6" core | T168 | T166
|  | 702.04 | Emulsified Asphalt | Distillation, Penetration @ 25 °C | 1/Project | Truck on Project | 2 Quarts | T40 | Certification T49, T59
Bituminous Concrete Pavement | 406.25 406.27 490.30 | 406.03 | Bituminous Concrete Pavement | AC Content /Gradation | Type D Certification | For certification-verification (C-V) purposes: Box Sample on Project | Dependent on mix type - see note 11 | T168 | T164 or T308 & T30
|  | 406.03 | Medium Duty Bituminous Concrete Pavement | AC Content /Gradation | Type D Certification
Non Mainline Paving
Side roads, Traffic Islands, Gutters, Curbs, Side Walks, Handwork, Drives & Aprons |  | 490.3 | Superpave Bituminous Concrete Pavement | Mixing Temperature | Type D Certification |  |  | T168
|  | 702.04 | Emulsified Asphalt | Distillation, Penetration @ 25 °C | Type A Certification | For C-V purposes: Truck on Project | 2 Quarts | T40 | Certification T49, T59
Bituminous Concrete Pavement Non Mainline Paving | 616.30 616.31 616.47 | 616.13 | Bituminous Concrete Gutters and Traffic Islands | AC Content / Gradation | Type D Certification | For certification-verification (C-V) purposes: Box Sample on Project | Dependent on mix type - see note 11 | T168 | T164 or T308 & T30
Side roads, Traffic Islands, Gutters, Curbs, Side Walks, Handwork, Drives & Aprons |  | 406.03 | Bituminous Concrete Curb Type A | AC Content / Gradation | Type D Certification
|  | 406.03a | Bituminous Concrete Pavement | AC Content / Gradation | Type D Certification
|  | 702.04 | Emulsified Asphalt | Distillation, Penetration @ 25 °C | Type A Certification | For C-V purposes: Truck on Project | 2 Quarts | T40 | Certification T49, T59
Structural Concrete | 501.32 501.33 501.34 541.21 541.22 541.25 541.40 | 501.03 541.03 | HPC Structural Concrete | Air | 1 per 50 cy (See Note 4) | on project, as close to point of deposit as possible | 1 ft3 for cylinders or wheelbarrow needed for all tests | T141 | T152
|  |  |  | Slump |  |  |  |  | T119
Superstructure |  |  | Structural Concrete | Temp |  |  |  | T141 | T309
|  |  |  | Unit weight(light weight) |  |  |  | T141 | T196
|  | 580.10 580.11 580.12 580.19 |  | Cylinders |  |  |  | T23 | T22
Substructure | 501.32 501.33 501.34 541.21 541.22 541.25 580.13 580.14 580.15 677.12 | 501.03 541.03 | HPC Structural Concrete | Air | 1 per 75 cy (See Note 5) | on project | 1 ft3 for cylinders or wheelbarrow needed for all tests | T141 | T152
|  |  |  | Slump |  |  |  |  | T119
Approach Slabs/Retaining Walls/Drilled Shafts/Mast Arm Supports/Overhead Sign Supports |  | 541.03 | Structural Concrete | Temp |  |  |  | T141 | T309
|  |  |  | Unit weight (light weight concrete) |  |  |  | T141 | T196
|  |  |  | Cylinders |  |  |  | T23 | T22
Note: For Mast Arm Supports and Overhead Sign Supports the bolt requirements below may also apply. |  | 677.13 | 678.17
|  | 677.22 | 679.21
|  | 677.23 | 679.22
678.15
Prestress/Precast Concrete9/Median Barriers | 510.21 510.22 510.23 540.10 | 510.05 | Concrete | Cylinder strength | per casting bed (note 7) | point of placement | 1 ft3 for cylinders or wheelbarrow needed for all tests | T 23 | T22
|  |  |  | Air content | per casting bed (note 8) |  |  | T141 | T152
|  |  |  | Temperature | per casting bed (note 8) |  |  | T141 | T309
|  |  |  | Slump (specified on approved mix design) | per casting bed (note 8) |  |  | T141 | T119
|  |  | Reinforcing Steel |  | See Reinforcing Steel Section
Structural Concrete | 616.27 616.28 616.45 618.10 618.11 621.45 | 541.03 | Structural Concrete | Air | 1/Project | on project | wheelbarrow | T141 | T152
|  |  |  | Slump |  |  |  |  | T119
Sidewalks/Curbs/Gutters6
Structural Steel | 506.50 506.55 506.56 506.57 506.60 506.75 | Project Special Provisions 714.05 714.06 714.12 714.13 | High Strength Bolts for Structural Steel | Rotational Capacity Test Wedge Test | 4 - Each combination of bolt production lot, nut lot, and washer lot (4 - Each combination Tension Control Assembly Bolt production lot or Direct Tension Indicator production lot if used) to be incorporated into the project for main member connections as designated in the Contract. | Original Manufacturer Shipping Container at the project or at fabrication facility | N/A |  | Rotational Capacity Test Specified in AASHTO M 164 M as modified in 714.05 Wedge Test per ASTM F 606
Bridge Railing | 525.22 525.23 525.31 525.33 525.34 525.40 525.41 525.42 525.43 525.44 | Project Special Provisions 714.07 | Anchor Bolts for Bridge Railing | Wedge Test | 2 - Each combination of anchor bolt production lot, nut lot, and washer lot to be incorporated into the project. | Original Manufacturer Shipping Container at the project or at fabrication facility | N/A |  | Tensile Strength Test ASTM F606 Verification Testing ASTM F606
Reinforcing Steel | 507.15 507.17 | 713.01 713.07 | Reinforcing Steel, Epoxy Coated Reinforcing Steel | Tensile testing, elongation | 1/100,000 lb/size/grade | Stockpile on Project | 5 ft |  | AASHTO T244
Mechanical Bar Connectors | 507.19 | 713.02 | Mechanical Splices for Bar Reinforcement | Tensile testing, elongation | 3 per size | Stockpile on Project | Connector length plus 12 inches of bar on each end |  | AASHTO T244
Over Head Traffic Sign Supports & Street Lighting | 677.12 677.13 677.22 677.23 677.25 679.xx | Project Special Provisions 714.09 | Anchor Bolts for Sign and Luminaire Poles | Tensile Proof Load Test Elongation Test | 2 - Each combination of anchor bolt production lot, nut lot, and washer lot to be incorporated into the project. | Original Manufacturer Shipping Container at the project or at fabrication facility | N/A |  | Tensile Strength Test ASTM F606 Verification Testing ASTM F606
Note: For Mast Arm Supports and Overhead Sign Supports the concrete requirements above may also apply.
|  |  | High Strength Bolts for Structural Steel | Rotational Capacity Test Wedge Test | 4 - Each combination of bolt production lot, nut lot, and washer lot (4 - Each combination Tension Control Assembly Bolt production lot or Direct Tension Indicator production lot if used) to be incorporated into the project for main member connections as designated in the Contract. | Original Manufacturer Shipping Container at the project or at fabrication facility | N/A |  | Rotational Capacity Test Specified in AASHTO M 164 M as modified in 714.05 Wedge Test per AASHTO M 164M
Paint for Pavement Markings | 646.20 to 646.32 | 708.08 | Waterborne Traffic Paint | Drying time | 1 / Batch | Original Container (tote) | 2, 1 pint (500ml) containers |  | ASTM D711
|  |  |  | Viscosity |  |  |  |  | ASTM D562
|  |  |  | Density |  |  |  |  | ASTM D1475
Underdrains | 605.10 to 605.23 | 704.16 | Drainage Aggregate |  | 1 / Project | On Project | 55 | T2 | T27
Notes: | (1) Testing procedures are AASHTO procedures unless otherwise noted.
(2) Sample size is in pounds unless otherwise noted. The sample size should be selected based on the maximum nominal aggregate size (See AASHTO T27, Section 7.1). For example, if the material visually passes a 2", 1.5", or 1" sieve then the sample size is 220 lbs, 165 lbs, and 110 lbs, respectively.
(3) For projects with more than 200 CY.
(4) Total placement for day split into equal sublots not to exceed 50 CY, test yardage chosen randomly. The test yardage is used to determine which load to test with proper sample collection techniques followed Check first load for temperature, slump and air content, this will not be counted as the acceptance test for the first sublot. If the first load is determined to be out-of-specification then the Contractor must test each consecutive load until 3 consecutive passing loads are tested. VTrans will check 4th consecutive load to verify.
(5) Check first load for temperature, slump and air content as an initial check. Acceptance sampling will be done every 75 CY, including the first load in the yardage count. If the first load, or any acceptance test, does not comply with VTrans' specifications then the Contractor must test each load until 3 consecutive passing loads are achieved. VTrans will check 4th consecutive load or last load, which ever happens first, to verify compliance.
(6) These materials are only required to be tested for Level 1 projects. Those items not identified are considered incidental have no materials testing requirements.
(7) Tests are to be performed by qualified plant personnel and witnessed by VTrans personnel. Minimum of six cylinders for determining detensioning, to be cured with the piece. Four specimens to determine 28 day and shipping strengths and are to be cured with the piece until it is stripped and then standard cured.
(8) Tests are to be performed by qualified plant personnel and witnessed by VTrans personnel. As a minimum, the first load as well as the load that the cylinders are fabricated from should be tested.
(9) Non-prestressed precast elements are exempt from acceptance testing and shall be furnished with a Type D certification.
(10) For projects less than 1250 CY of subbase material the Agency shall be responsible for the testing and projects over 1250 CY the Contractor is responsible for the determination of the target density. For each material source; subbase materials shall be sampled and tested once for the first 1250 CY and then once every 3000 CY thereafter.
(11) The sample size for HMA depends upon the nominal maximum aggregate in the mix, see following table. Minimum sample sizes are in accordance with AASHTO T168 and are suitable for routine testing. However, actual sample size is dependent upon the type and number of tests to which the material is to be subjected.
| Mix Type: |  |  | MS | I / IS | II / IIS | III / IIIS | IV / IVS | V / VS
| Maximum Nominal Aggregate Size, in: |  |  | 1 1/2" | 1" | 3/4" | 1/2" | 3/8" | 3/16"
| Minimum Sample Size, lbs: |  |  | 25 | 20 | 16 | 12 | 8 | 4