## Spotcheck Form
MAB CONSTRUCTION INSPECTION - SPOTCHECK FORM 8/29/2019 Version
PROJECT TOWN AND NUMBER:
COMMON NAME:
PROJECT MANAGER/SUPERVISOR:
CONSTRUCTION INSPECTION FIRM: |  | RESIDENT ENG /Cell Phone:
QA INSPECTOR / DATE OF SITE VISIT: |  |  |  | Indicate
1.DAILY RECORDS |  |  | OK or Add note |  | Notes:
A. Neat and complete records of work performed, Daily work Reports, issues, solutions, progress photos
B. Documentation of installed quantities with reference to contract pay item numbers
C. Civil rights poster board clearly visible and complete? Complete Specs and plans on site?
D. Verify material Quantities with slips from Paving trucks, concrete delivery, etc.
E. EPSC measures in place and checked/maintained, as needed. Contact Dig-safe in timely manner.
F. Verify all workers/visitors etc. have necessary personal protective gear to be on site
2.MATERIAL TESTING /CERTIFICATIONS
A. Material certifications and testing data received & in file, prior to installation and payment.
B. Confirm that all Iron and steel (over threshold limit) complies with "Buy America."
C. Have necessary permits/approvals been obtained for any offsite waste borrow and staging areas?
D Any weld, or compaction testing required? Any Shop Drawings sent to design engineer for review?
3.TRAFFIC MANAGEMENT PLAN/TRAFFIC CONTROL
A. Have flagger certifications been verified?
B. Note TC measures at beginning and end of shift (or more freq. as required)
C. Work Zone accommodations/signs for pedestians and bicyclists?
D. Photo documentation of traffic control measures in high volume areas
E. Planned coordination with adjacent construction projects by VTRANS etc. as appropriate
F. Site specific traffic control plan submitted by contractor?
4. CHANGE ORDERS
A. Provide detailed independent cost analysis along with other CO documents?
B. CO Fully Executed prior to work being performed or is it an Emergency situation?
5. PAYROLL AND SUBCONTRACTORS
A. Are proper certified payrolls submmitted correctly and on time and include Side 2 of Wh347 payroll form?
B. Have you confirmed Davis-Bacon wage rate are being met , if they apply?
C. Provide documentation of approval of SubContractors from project files, also DBE firms
D. Prime contractor reporting monthly to RE with MAB Prompt Pay Monthly Report Form?
6. ENVIRONMENTAL PERMITS / UTILITY CLEARANCES
A. Are copies of key documents in file and is site in compliance with any permit conditions?
B. Have waste borrow & staging areas been approved for use by VAOT environmental section?
7. AS-BUILT DRAWINGS
A. Are a set of drawing being marked up with field changes etc. as project progresses?