## Example
Attachment G:
2024 Additional Funding Worksheet
| Applicant Name: | Town of Anytown
| Project Title: | D St. Sidewalk
Determining Make Up Funding for an Existing Project
| Original Award (including Local share) | 650000
| Engineering Expenses to Date | 50000
| Project Management Expenses to Date | 25000
| ROW expenses to Date | 10000
| Amount Remaining from original award | 565000
| Balance of Engineering contract to be billed | 20000
| Balance of Project Management to end of project | 15000
| Balance of ROW expenses anticipated | 5000
| Estimated Construction Cost | 525000
| Estimated Construction Inspection Cost | 50000
| Total Cost to Complete Project | 615000
| Amount Remaining in Grant Award (or deficit) | -50000

## Annotated Template
Attachment G:
2024 Additional Funding Worksheet
| Applicant Name: | Town of Anytown | Fill in applicant name
| Project Title: | D St. Sidewalk | Fill in project title to match rest of application
Determining Make Up Funding for an Existing Project
| Original Award (including Local share) | 650000 | Fill in fields in the table based on the descriptions to the left.
| Engineering Expenses to Date | 50000
| Project Management Expenses to Date | 25000
| ROW expenses to Date | 10000
| Amount Remaining from original award | 565000 | This will total automatically based on input above
| Balance of Engineering contract to be billed | 20000 | Fill in fields in the table based on the descriptions to the left.
| Balance of Project Management to end of project | 15000
| Balance of ROW expenses anticipated | 5000
| Estimated Construction Cost | 525000
| Estimated Construction Inspection Cost | 50000
| Total Cost to Complete Project | 615000 | This will total automatically based on input above
| Amount Remaining in Grant Award (or deficit) | -50000 | This will total automatically based on input above - if figure shows up in parenthesis and red, then that is a shortfall.

## Blank Form
Attachment G:
2024 Additional Funding Worksheet
Applicant Name:
Project Title:
Determining Make Up Funding for an Existing Project
| Original Award (including Local share) | 0
| Engineering Expenses to Date | 0
| Project Management Expenses to Date | 0
| ROW expenses to Date | 0
| Amount Remaining from original award | 0
| Balance of Engineering contract to be billed | 0
| Balance of Project Management to end of project | 0
| Balance of ROW expenses anticipated | 0
| Estimated Construction Cost | 0
| Estimated Construction Inspection Cost | 0
| Total Cost to Complete Project | 0
| Amount Remaining in Grant Award (or deficit) | 0