## Slide 1: Stowe BO 1446(37) Selectboard Presentation Town Highway 43 – Bridge #51 over Miller Brook
March 25, 2019

## Slide 2: Introductions
Carolyn Carlson, P.E.
VTrans Design Project Manager
Cory Burrall, P.E.
VTrans Project Design Engineer
Andrew Lemieux
VTrans Design Engineer

## Slide 3: Purpose of Meeting
Provide an update to project development
Project overview and existing conditions
Proposed design and conceptual plans
Temporary bridge and maintenance of traffic
Discuss project impacts
Cost estimates
Project schedule and timeline
Provide an opportunity to ask questions and voice any concerns

## Slide 4
Location Map

## Slide 5
Bridge 51
Nebraska Valley Road
TH 3

## Slide 6: VTrans Project Development Process
Project Definition
Project Design
Construction
Project
Funded
Project
Defined
Contract
Award
Quantify areas of impact
Environmental permits
Develop plans, estimate and specifications
Right-of-Way process
We are here
Identify resources & constraints
Evaluate alternatives
Public participation
Build Consensus

## Slide 7: Project Overview

## Slide 8
Bridge #51
Roadway Classification – Local Road (Class 3 TH)
Bridge Type – 54’ Span Rolled Beam Bridge
Ownership – Town of Stowe
Constructed in 1948
Looking East over Bridge

## Slide 9
Existing Conditions - Bridge #51
Deck Rating 4 (Poor)
Superstructure Rating 6 (Satisfactory)
Substructure Rating 5 (Fair)
12-month Inspection Frequency
Deck & Superstructure Deterioration – Bedrock Outcrop @ Eastern Abutment

## Slide 10: Design Criteria and Considerations
ADT of 430; DHV of 60
% Trucks: 3.4
    Truck volume and nearby gravel pit
Waterway clearance
    Low beam elevation less than 10 ft above river
Design speed of 35 mph
Site limitations and embankment for temporary bridge
    Ledge removal
    One Lane alternating with Traffic Signal
Right-of-Way needed; Utility relocation not needed
Adjacent property owners
Additional properties, businesses, archaeological sensitive areas, and recreational use

## Slide 11: Proposed Bridge Replacement – Bridge #51
Full Bridge Replacement on Alignment with Traffic Maintained on Upstream Temporary Bridge
    Maintain existing centerline of road
    New concrete deck on 4 galvanized steel rolled beams
    Widen Bridge to 9’/3’ typical to match corridor and provide bicycle accommodations
      Exceeds the minimum standard (9’/2’)
    Meets all geometric criteria - <1% slope over the bridge
      2% roadway crown and fascia mounted bridge rail to promote runoff
    Eastern abutment founded directly on bedrock with spread footing
    Western abutment on piles
    80 year design life
    Construction – Summer 2022

## Slide 12: Proposed Typical Section

## Slide 13: Proposed Profile

## Slide 14
Temporary Bridge
  One Lane Temporary Bridge with Traffic Signal
  Upstream Temporary Bridge as preferred by Town
  Temporary Bridge will require temporary ROW acquisition
  Will require extensive embankment excavation due to site limitations

## Slide 15: Proposed Bridge Layout
Temporary Bridge Preferred Option - Bridge #51
Upstream temporary has greater impacts and potential impacts to Northern Long Eared Bat Habitat
Longer Temporary Bridge required, solid rock excavation, additional cost
Notes: original

## Slide 16: Cross Section of Slope Impact Western Abutment 1
Notes: Mike considering blocks

## Slide 17: Cross Section of Slope Impact Eastern Abutment 2
Notes: Mike considering blocks

## Slide 18: Cost Estimates
Stowe BO 1446(37) Cost Estimate | 
Total Project Costs (Including E & C) | $1,942,231
Town Share | $194,223
Town % | 10%
Project Development Duration | 4 years
Construction Duration | Approximately 6 months (April to October)
Closure Duration (If Applicable) | N/A
Typical Section - Bridge (feet) | 3-9-9-3
Hydraulics | Meets Standard
Utility | No Change
ROW Acquisition | Yes
Design Life (Years) | 80
Notes: ?

## Slide 19: Project Schedule
Stowe BO 1446(37) Development Schedule | 
Scoping | Complete
Conceptual Plans | Complete
Preliminary Plans | December 2019
Permitting | Winter 2020
Right-of-Way Clear | Spring 2021
Final Plans | April 2021
Contract Plans | July 2021
Bid Advertisement | September 2021
Contract Award | October 2021
Construction | April 2022 – October 2022

## Slide 20: Stowe BO 1446(37) Questions and Comments Town Highway 43 – Bridge #51 over Miller Brook
March 25, 2019
For more information:
https://outside.vermont.gov/agency/vtrans/external/Projects/Structures/12J660