## Sheet1
Date: | 2016-04-13 | Rev: 06/01/16 | Rev: | Rev: | Rev:
VTrans N Hero Grand Isle Bridge
Functional Assignments:
ENV | Permit/Environmental
DES | Design
ROW | Right-of-Way
CONST | Construction
UTIL | Uitlity
POLIT | Political
Risk # | Functional Assignment | Threat/Opportunity | Type of Risk | Mitigation |  | Who | Probability | Impact | Cost (Low) | Cost (High)
1 | CONST | Traffic (Vehicle) Accidents | Disrupts construction, damage to bridges | Mitigated with an Emergency Management Plan in conjunction with TMP. |  | Cianbro | Low | Low
2 | CONST | Late Notice to Proceed (NTP) | Results in extra construction season, added costs | VTrans assures funding is in place, staff are involved in the project. Cianbro provide sample CPM Schedule early. Have all precontract items complete 12/31/16. |  | VTrans/Cianbro | Low | High
3 | DES | Weathered Bedrock Removal | Significant redesign | Clearly defining removal and inspection requirements |  | HDR | Low | Low |  |  | HDR to define requiremetns in plans and specifications
4 | POLIT | VTrans Priority Change | Funding Unavailable | Verify funds are programmed for correct Construction timeframe |  | VTrans | Low | Low
5 | POLIT | Unable to get GMP | Schedule and cost impact | Continued open & honest collaboration. Callibration Meetings successful |  | All | Low | High
6 | POLIT | Change of key CMGC personnel prior to or during construction | Slows the CMGC Processs | Good documentation of all meetings / decisions |  | All | Low | Med
7 | CONST | Claims for differing site conditions | Increase Costs, Schedule Delays | Early detailed site investigations |  | HDR | Low | High |  |  | Performed additional boring and site ivnestigations - results included in plans
8 | CONST | VOSHA violations | Schedule / Cost | Early identification. Strong Safety Practices. |  | Cianbro | Low | Low
9 | CONST | Coast Guard violations | Schedule / Cost | Proper procedures and notifications to CG |  | Cianbro | Low | Low
10 | DES | Unclear basis of payments and scope of work for pay items | Schedule / Cost | Due dilgence on Deisgner for clear specifications. Cianbro to review before GMP. |  | HDR / VTrans | Low | High |  |  | Unlikely due to Contractor revierw of plans/specs etc.
11 | POLIT | Unclear Coast Guard Regulations (specific to bridge closure and channel restriction) | Schedule / Cost | Early & frequent coordination with CG |  | VTrans | Low | High
12 | DES | Designer Errors | Schedule / Cost | Follow preapproved Design Quality Management Program |  | HDR | Low | Med
13 | DES | Lack of knowledge by Vtrans with respect to drawbridge terminology and specifications (includes internal reviews of submittal drawings) | Slower Design Process, Confusion in the field | Preconstruction, Pre-Activity Meetings, Education of Staff Involved |  | All | Low | Low
14 | CONST | Procurement delays for mechanical, electrical, & structural equipment | Schedule / Cost | Cianbro to contact suppliers early. HDR share design information as early as possible. |  | HDR / Cianbro | Low | Med |  |  | Contractor advance knowledge of design and cost reconciliation forces contractor to advance negotiate price and delivery. Extra season due to Temporary Bridge as well.
15 | POLIT | Lack of coordination with operations or other bureaus leads to unrealistic expectations | Schedule / Cost | Open Continued Communications |  | All | Low | Low |  |  | Mitigated during design phase
16 | CONST | Mutually Agreed Upon Base Schedule | Schedule / Cost | Open Continued Communications, Incentives and Disincentives |  | Cianbro | Low | High
17 | UTIL | Unforeseen utility conflicts - utilities not mapped out yet, drainage, buried electric gas etc. | Schedule / Cost | Proper Field Identification of Utilities |  | HDR | Low | Med |  |  | VTrans is working with VEC, Fairpoint, and Comcast to locate utilities
18 | CONST | Existing commnication and power cables damaged during construction | Schedule | Proper Field Identification of Utilities / Proper Training |  | HDR / Cianbro | Low | Low |  |  | Currently mitigating, relocation not done yet
19 | DES | 100 year flood and wave impact to design and construction | Location of Electrical Equipment, Life Cycle Cost | Use latest FEMA maps + 2' |  | HDR | Low | Med |  |  | Cianbro to look at delay to construction schedule | Lake levels during Irene?
20 | POLIT | Public challenges to project during permitting process | Design Changes, Schedule, Costs | Use of Public Outreach Program |  | HDR / VTrans | Low | Med |  |  | still possible
21 | POLIT | Delays from Public challenges impacts schedule, cost of design, construction | Design Changes, Schedule, Costs | Use of Public Outreach Program |  | HDR / VTrans | Low | Med |  |  | still possible due to permitting
22 | POLIT | Historical/ Public interest groups unhappy with final design – political pressure applied (No new public meetings to review the redesigned plans) | see #21 | Tentatively Schedule Public Outreach Meeting for October |  | HDR / VTrans | Low | Med |  |  | delete
23 | ENV | Environmental issues associated with unknown endangered species moving into construction area and temporary bridge location (i.e. turtles come to visit) | Schedule / Cost | Complete NEPA, Complete project before species surveys expire |  | HDR / VTrans | Low | High |  |  | Existing bats, mussels are outside of temporary bridge limits???
24 | DES | Construction limits relative to environmental permit constraints/conditions. Restriction with temporary structures outside of structure foot print | Schedule / Cost | Confirm CG answer on closing part of channel. CG Meeting during design |  | HDR / VTrans | Low | MH |  |  | Will be defined in Coast Guard Permit
25 | CONST | Scheduled allowable construction period for project too restrictive – LD’s (Based upon the LD’s presented in WP2 this could be a big issue) | Cost | Use CMGC Process |  | All | Low | Low |  |  | Is this still a risk with temp bridge?
26 | CONST | Need to plan on being out of water before winter in order to avoid having cofferdams designed to withstand ice flow/ damage. | Schedule / Cost | Evaluate Construction Schedule |  | All | Low | Low
27 | CONST | Escalation costs over 6 years (2 year design, 3.5 yrs construction) | Cost | Stored Material / Procurement Payments during Construction |  | All | Med | Low |  |  | Need to discuss cash flow realities for Movable Bridge projects
28 | CONST | Craft wage rate/ pay scale not sufficient to attract skilled tradespeople (current DB rates are too low to attract Millwrights and other specialty trades needed to construct movable bridge. Not a problem in the past because this is the first movable bridge in VT. Will need to pay higher rates.) | Cost | CMGC & Cost reconcilliation process |  | All | High | Low
29 | DES | Operation and maintenance requirements during construction (number of operators, hours, training) | Cost | Define in Special Provisions |  | HDR / Vtrans | Low | Low |  |  | HDR prepared a DRAFT Special Provision, should be mitigated prior to construction
30 | CONST | Night work being required to maintain construction schedule (nighttime work differential) | Schedule / Cost | Identified in the Schedule. Include float in the schedule. Properly staff project. |  | Cianbro | Low | Med
31 | CONST | Delays in the review process or approval process during construction. | Schedule / Cost | Having Enough Qualified Staff to review submittals. Have a well defined process for reviews. Submit complete coherent packages. Direct communication. |  | All | High | Med
32 | CONST | Schedule delays caused by failure of vendor/fabricator to meet agreed to project schedule milestones | Schedule (all) / Cost (Cianbro) | Agressively monitor fabricators |  | Cianbro | Med | Med
33 | CONST | Failure to identify non-Buy American compliant materials – Example Brake components | Schedule / Cost | Ask for exemptions early |  | Cianbro | Low | Low
34 | CONST | Potential damage to existing structure – due to boat collision | Safety / Schedule / Cost | Marine Traffic Control Devices |  | Cianbro | Low | Low |  |  | Marine traffic control plans to be developed
35 | CONST | Boat crashes into construction equipment/ existing bridge/ new bridge | Safety / Schedule / Cost | Marine Traffic Control Devices |  | Cianbro | Low | High |  |  | Marine traffic control plans to be developed
36 | CONST | Permanent or Temporary Bridges stuck in open position – need emergency services back-up plan | Stakeholder | Have a plan in place. |  | Cianbro | Low | Low |  |  | Redundant drive and emergency action plan in place
37 | CONST | Existing bridge fails to open/close during construction (old bridge that has history of issues, we are only put a band-aid. Operation and maintenance is something we can price, but unknown structural issues are out of the contract) | Stakeholder | Complete Intirim Repairs. |  | All | Low | Low |  |  | Temp bridge mitigates this issue
38 | CONST | Interim Repair(s) Equipment failure. | Stakeholder | Perform Maintenance during construction |  | Cianbro | Low | Low
39 | ENV | Unknown Hazardous materials discovered during construction | Schedule / Cost | Have a Haz Mat Plan in place. Include Haz Mat item in contract. |  | All | Low | Med |  |  | Unlikely due to advance investigations, mitigated in Spec Book
40 | CONST | Obstructions encountered during installation of guardrail posts or abutment piles. | Cost | Include in Specifications |  | HDR / VTrans | Low | Low |  |  | Existing guardrail is present, shouldn't be an issue, delete?
41 | CONST | Handling oversized components (water - multiple handling, land - extensive permitting and issues with ongoing construction etc.) | Schedule / Cost | Collaborate on Design of Elements. Include in Schedule |  | HDR / Cianbro | Low | Med |  |  | Added splice to Bascule Girders
42 | CONST | Impact to cost & schedule due to extreme weather events | Schedule / Cost | Include Float in schedule |  | Cianbro | High | High
43 | DES | Existing bridge condition dictates accelerated design and construction - poor condition of existing structure. | Schedule / Cost | Monitor Health of Bridge. Identify critcal bridge elements. Verify load rating of 2 girder system. Preconstruction structural inspection. |  | HDR | Low | Med
44 | DES | Key decision making protocol not in place for CMGC | Schedule / Cost | Have a clearly defined protocol in place |  | All | Low | Low
45 | DES | Design rework due to CM/GC input | Schedule / Cost | Open Continued Communications |  | All | Low | Low |  |  | Archeological Resource still a concern
46 | DES | Not including Contractor in development of the specifications. | Schedule / Cost | Open Continued Communications |  | All | Low | Med
47 | DES | Structural Steel Failure of Existing Bridge | Schedule / Cost | Complete Item # Above |  | HDR | Low | High
48 | CONST | Dewater the bascule Pier | Schedule / Cost | Verify thickness of the tremie seal will resist bouyant forces. Use water tight details for connecting cofferdam to existing footings / tie beams |  | HDR / Cianbro | Low | High
49 | CONST | Disposal sites cannot accept demolition debris | Schedule / Cost | Identify adequate disposal site(s) |  | Cianbro | Low | Med
50 | CONST | Existing swing span bridge foundations are in conflict with the temporary bridge foundations | Schedule/Cost | Excavator can remove prior to cofferdam, probing for existing timber crib |  | Cianbro | Low | High |  |  | Change pier size or remove conflict? - Design mitigates interference
51 |  | Preliminary sampling of sediments for hazardous materials |  |  |  |  | Low | Med
52 | CONST | Adnormal Winter Weather | Schedule Cost | Build Float into construction schedule |  |  | Med | Med
53 | ENV | Archeological artifact location causes change in temp bridge alignment and construction means and methods | Schedule/Cost | Survey to be conducted in spring of 2017 |  | HDR/Vtrans | HIGH | HIGH
54 | CONST | Subsurface/ground elevation at temporary bridge requires anchors in Acrow Bridge Pier Piles | Schedule/Cost | Pricing a contingent RISK item for Anchors |  | Cianbro | Med | High
55 | CONST | 1 Year On-Call Warranty Service - Specials Provisions Electrical Page 65 | Schedule/Cost | Remove this special provisions section from the contract. Vtrans hire a local vendor to determine if the issue is a warranty issue. |  | Vtrans | High | High
56 | CONST | Pavement Repair on Temporary Bridge | Schedule/Cost | Add a bid item for pavement replacement by the unit price |  | Vtrans | High | High
57 | UTIL | Directional Bore Utility Lines go Through New Pier | Schedule/Cost | New directional bore needs to be installed before cofferdam installation |  | Vtrans | High | High
58 | UTIL | Permits required for new well and septic | Schedule/Cost | HDR Coordinate with Vtrans |  | Vtrans | Med | Med
59