## Level 1 Risk Register
LEVEL 1 - RISK REGISTER |  |  |  | Project Name: | Bristol BF 021-1(33), VT Route 116, Bridge 12 over Baldwin Creek |  | Deck Replacement ON Alignment in phases |  | Project Manager | Carolyn Carlson
Risk Identification | [6 empty] | Risk Rating |  | Risk Response
Status | ID # | Type | Category | Title | Risk Statement | Current status/assumptions | Priority Rating | Rationale for Rating | Strategy | Response Actions | Risk Owner | Updated
Active | 1 | Threat | Construction | Aerial Utilities Move | If Utilities are not moved in time, then construction could be delayed |  | High | 2 year development duration
Active | 2 | Threat | Construction | Deck Removal | If shear studs are present, then removal of the deck could take longer than anticipated | Shear studs are not shown on record plans | Medium
Active | 3 | Threat | Construction | Product Quality - Phased Construction | If traffic is phases, then the quality of the final product could be hindered due to concrete joints |  | Low
Active | 4 | Threat | Construction | Safety During Construction | If construction is phased, then there is decreased safety to workers who have to work around traffic |  | High
Active | 5 | Threat | Environmental | Archaeoloical Resoures | If construction goes outside the conceptual limits, then arhaeologically sensative resources could be impacted which could be costly |  | Low
Active | 6 | Threat | Construction | Traffic Congestion | If traffic is phased with decreased speed limit, then traffic congestion could occur through the construction area | Speed limit through the project area should be decreased by 10 mph for traffic safety. Due to the AADT, a minimal drop in LOS is expected | Low
Active | 7 | Threat | ROW | Park and Ride Landowner Dispute | If the Park and ride is impacted, then project development could be delayed | There is a legal issue regarding the land owner at the park and ride and who the landowner is, no impacts are expected at this time | Low
Active | 8 | Threat | Design | Bridge Joint Type | If the Joint type is not selected properly, then a bump could exist going on and off the bridge | Both a VT Joint and utilizing two plug joints should be considered | Low
Active | 9 | Threat | Construction | Existing Diaphragms | If construction is phased, then the existing diaphagms will have to be cut in order to maintain traffic on one side of the bridge. | Traffic will be phased and this should be accountd for during the design phase | Low
Active | 10 | Threat | PM | Project Advertisement | If the project is not advertised on time, then construction year could be delayed |  | Low

## Level 2 Risk Register
LEVEL 2 - RISK REGISTER |  |  |  | Project Name: | Example Project |  | DIST- EA | 08-1234 | Project Manager | PM Person
Risk Identification | [6 empty] | Risk Assessment | [5 empty] | Risk Response
Status | ID # | Type | Category | Title | Risk Statement | Current status/assumptions | Probability | Cost Impact | Cost Score | Time Impact | Time Score | Rationale | Strategy | Response Actions | Risk Owner | Updated
Active | 1 | Threat | Construction | Aerial Utilities Move | If Utilities are not moved in time, then construction could be delayed | 0 | High | 2 year development duration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Active | 2 | Threat | Construction | Deck Removal | If shear studs are present, then removal of the deck could take longer than anticipated | Shear studs are not shown on record plans | Medium | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Active | 3 | Threat | Construction | Product Quality - Phased Construction | If traffic is phases, then the quality of the final product could be hindered due to concrete joints | 0 | Low | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Active | 4 | Threat | Construction | Safety During Construction | If construction is phased, then there is decreased safety to workers who have to work around traffic | 0 | High | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Active | 5 | Threat | Environmental | Archaeoloical Resoures | If construction goes outside the conceptual limits, then arhaeologically sensative resources could be impacted which could be costly | 0 | Low | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Active | 6 | Threat | Construction | Traffic Congestion | If traffic is phased with decreased speed limit, then traffic congestion could occur through the construction area | Speed limit through the project area should be decreased by 10 mph for traffic safety. Due to the AADT, a minimal drop in LOS is expected | Low | 0 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0
Active | 7 | Threat | ROW | Park and Ride Landowner Dispute | If the Park and ride is impacted, then project development could be delayed | There is a legal issue regarding the land owner at the park and ride and who the landowner is, no impacts are expected at this time | Low | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Active | 8 | Threat | Design | Bridge Joint Type | If the Joint type is not selected properly, then a bump could exist going on and off the bridge | Both a VT Joint and utilizing two plug joints should be considered | Low | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Active | 9 | Threat | Construction | Existing Diaphragms | If construction is phased, then the existing diaphagms will have to be cut in order to maintain traffic on one side of the bridge. | Traffic will be phased and this should be accountd for during the design phase | Low | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Level 3 Risk Register
LEVEL 3 - RISK REGISTER |  |  | Project Name: | Example Project |  | DIST- EA |  | 08-1234 | Project Manager | PM Person
Risk Assessment
Risk Identification | [5 empty] | Probability |  | Cost Impact ($) |  |  |  | Time Impact (days) |  |  |  | Rationale | Risk Response
Status | ID # | Category | Title | Risk Statement | Current status/assumptions | Low | High | Low | Most likely | High | Probable | Low | Most likely | High | Probable |  | Strategy | Response Actions | Risk Owner | Updated
Active | 160 | Design | Survey File | Inaccuracies or incomplete information in the survey file could lead to rework of the design. |  | 40 | 60 | 100000 |  | 300000 | 100000 | [5 empty] | #REF! | #REF! | #REF! | #REF!
Active | 161 | Environmental | Challenge to EIR | Potential lawsuits may challenge the environmental report, delaying the start of construction or threatening loss of funding. |  | 0 | 10 | 500000 | 800000 | 1200000 | 42000 | 60 |  | 150 | 5.25 |  | #REF! | #REF! | #REF! | #REF!
Active | 162 | R/W | Delay of R/W Acquisition | Due to the large number of parcels and businesses, may have to use the condemnation process to acquire R/W, which could delay start of construction by up to one year, increasing construction costs and extend the time for COS. |  | 40 | 60 | 500000 | 750000 | 2000000 | 542000 | 180 |  | 365 | 136.25 |  | #REF! |  | #REF! | #REF!
Active | 163 | Construction | Buried Objects | Unanticipated buried man-made objects uncovered during construction require removal and disposal resulting in additional costs. |  | 20 | 40 | 200000 |  | 400000 | 90000 | [5 empty] | #REF! | #REF! | #REF! | #REF!
Active | 164 | Design | Supplemental EIR | A design change that is outside of the parameters contemplated in the Environmental Document triggers a supplemental EIR which causes a delay due to the public comment period. |  | 10 | 30 | 100000 | 200000 | 400000 | 47000 | 0 |  | 60 | 6 |  | #REF! | #REF! | #REF! | #REF!
Active | 165 | Environmental | Nesting birds | Nesting birds, protected from harassment under the Migratory Bird Treaty Act, may delay construction during the nesting season. |  | 0 | 20 | 150000 |  | 300000 | 23000 | 0 |  | 30 | 1.5 |  | 0 | 0 | 0 | 0
Active | 166 | R/W | Additional R/W | Due to the complex nature of the staging, additional right of way or construction easements may be required to complete the work as contemplated, resulting in additional cost to the project. |  | 40 | 60 | 500000 | 750000 | 1000000 | 375000 | [5 empty] | 0 | 0 | 0 | 0
Active | 167 | Construction | Hazardous Materials | Hazardous materials encountered during construction will require an on-site storage area and potential additional costs to dispose |  | 20 | 40 | 100000 |  | 300000 | 60000 | [5 empty] | 0 | 0 | 0 | 0

## Level 2 Risk Matrix
Impact Definitions
Rating --> | Very Low | Low | Moderate | High | Very High
Cost Impact of Threat | Insignificant cost increase | <5% cost increase | 5-10% cost increase | 10-20% cost increase | >20% cost increase
(CO + COS)
Cost Impact of Opportunity (CO + COS) | Insignificant cost reduction | <1% cost decrease | 1-3% cost decrease | 3-5% cost decrease | >5% cost decrease
Schedule Impact of Threat | Insignificant slippage | <1 month slippage | 1-3 months slippage | 3-6 months slippage | >6 months slippage
Schedule Impact of Opportunity | Insignificant improvement | <1 month improvement | 1-2 months improvement | 2-3 months improvement | >3 months improvement
Probability | 1–9% | 10–19% | 20–39% | 40–59% | 60–99%
Risk Matrix
Probability Rating | 5 – Very High
4 – High
3 – Moderate
2 – Low
1 – Very Low
|  | 1 | 2 | 4 | 8 | 16
|  | Very Low | Low | Moderate | High | Very High
Impact Rating
Low Risk
Moderate Risk
High Risk