## Slide 1
Readsboro BF 0102(16)
VT Route 100 Bridge #25 Replacement Project
Readsboro, Vermont Presented by VTrans & VHB
March 21, 2018
© VHB, Inc.

## Slide 2: Meeting with you today
Carolyn Carlson
VTrans Project Manager
Scott Burbank
VHB Project Manager
Megan Ooms
VHB Project Engineer

## Slide 3: Meeting Overview
Project Objectives
VTrans Project Development Process
Existing Conditions
Proposed Bridge
Traffic Control During Construction
Schedule
Questions

## Slide 4: Project Objectives
Coordinated replacement of the bridge
Minimization of disruptions to the public
Minimize impacts to:
  Environmental Resources
  Historic and Archaeological Resources
  Right-Of-Way (ROW)
  Utilities

## Slide 5: VTrans Project Development Process
Phase A: Project Definition
Phase B: Project Design
Phase C: Construction – Anticipated Late Spring of 2021
Completed
Initiated

## Slide 6: Existing Conditions - Bridge Location
Notes: Located over Deerfield River
Depot St to the West
Phelps lane and Tunnel St to the East

## Slide 7: Existing Site Conditions
Notes: Driving east toward the center of town
Driving west from town
Elevation views of both north and south show deterioration
  Waterline on north side can be seen

## Slide 8: Existing Site Conditions
340’ Long by 38’-9” Wide Bridge over the Deerfield River
  2-105’ spans and 1-130’ span in the middle
Cast-in-place concrete abutments and piers
Curve at the east end
Town roads on either side
  Phelps Lane to the west
  Depot Street to the east
From last Inspection performed in 2017:
  Deck: 3 (Serious)
  Superstructure: 4 (Poor)
  Substructure: 6 (Satisfactory)

## Slide 9: Existing Site Conditions: Deck
Notes: Here you can see some examples of why the deck is rated a 3 for serious condition
The underside of the deck exhibits concrete spalling and rusting and deteriorating reinforcement
The topside of the deck shows both longitudinal and transverse cracking as well as general wear of the surface. Cracking is prominent throughout the length of the deck and will only continue to deteriorate

## Slide 10: Existing Conditions: Superstructure
Notes: Here you can see examples of why the superstructure was rater a 4 for Poor condition
The main girder shows severe section loss: full thickness loss
Main bracing members show rusting and section loss
Cracked members are also present including this connection angle which has a crack highlighted in orange.

## Slide 11: Existing Site Conditions: Substructure
Notes: The substructure was rated a 6 for Satisfactory but you can see several cracks and concrete spalling throughout the abutments and piers
In several locations the cracks are fairly wide with areas of more significant concrete spalling

## Slide 12: Existing Site Conditions
Fracture Critical Structure
Notes: Existing bridge is a Fracture Critical Structure
  Only 2 Girder System
  Loss of 1 Girder leads to Structural Failure
Non-failure critical structures are designed with more than two girders as a redundant system so that the loss of one girder doesn’t lead to entire structure failure for safety reasons.

## Slide 13: Proposed Bridge
Design Criteria
  Bridge and Roadway Alignment
  Curvature Design
  Right-of-Way Impacts
  Design Speed
  Scour
  Abutting Land Use
  Historical/Archaeological Resources
Design Considerations
  New Light Poles
  Historic Plaque

## Slide 14: Proposed Bridge
287’-0” Long by 35’-6” Wide Bridge (33’-6” Rail-to-Rail)
  Single span-no piers
Superstructure
  Steel Plate Girder Bridge with Concrete Deck
Substructure
  Semi-Integral Abutment on Both Sides
  Abutment on East is on Ledge
  Abutment on West is on piles

## Slide 15: Project Limits
Notes: New Sidewalk from Tunnel St to Depot St.
  Coordinating with other sidewalk project planned for the next year
Utility relocations

## Slide 16: Proposed Bridge

## Slide 17: Proposed Bridge
Steel Plate Girder Bridge with Concrete Deck

## Slide 18: Proposed Bridge
Semi Integral Abutment
(SHRP2 Project R04)

## Slide 19: Proposed Bridge
Typical Bridge Section
Notes: Proposed waterline

## Slide 20: Proposed Bridge- Retaining Walls
Two Types of Retaining Wall Proposed
  Pile and Lagging
  T-Wall or MSE Wall
Notes: 200+ foot retaining wall
Once the wall type is selected we will get input from the town on aesthetic treatments

## Slide 21
T-Wall or MSE Wall

## Slide 22
Pile and Lagging Wall

## Slide 23: Traffic Control- Overview
Staged Construction Methods
  Alternating One-Way Traffic with temporary Traffic Signals
  Extended Weekend Closures with Detour
Two Construction Seasons
No Temporary Bridge
  Saves Town Money on Waterline Relocation
Temporary Pedestrian Access provided with one-way alternating traffic until Permanent Access is Available

## Slide 24: Traffic Control During Construction: PHASE 1A
Notes: OFF ALIGNMENT
Traffic on existing bridge

## Slide 25: Traffic Control During Construction: PHASE 1B

## Slide 26: Traffic Control During Construction: PHASE 1B

## Slide 27: Traffic Control During Construction: PHASE 1B

## Slide 28: Traffic Control During Construction: PHASE 1B

## Slide 29: Traffic Control During Construction: PHASE 2 DEMOLITION

## Slide 30: Traffic Control During Construction: PHASE 2A

## Slide 31: Traffic Control During Construction: PHASE 2B

## Slide 32: Traffic Control During Construction: PHASE 2B

## Slide 33: Traffic Control During Construction: PHASE 2C

## Slide 34: Traffic Control- Detour

## Slide 35: Traffic Control-Detour
Considerations:
  Access to Emergency Services
    Mutual Aid
    Alternate Location for Ambulance/Fire Truck on East Side of Bridge
  Access to Hospitals in Bennington & Brattleboro
  Coordination will be made with Town Events

## Slide 36: Schedule
Preliminary Plans & Permitting – Winter 2017 to Spring 2018
Final Design – Summer 2018 to Spring 2019
Right-of-Way Complete – Fall 2018
Bid Advertisement – Fall 2020
Contract Award – Winter 2020
Construction – Sequenced throughout 2021 and 2022

## Slide 37
Thank You. Questions or Comments?