## Slide 1: Orleans Village BF 0310(7) Project Update Presentation VT Route 58 (Main Street/TH 1) – Bridge #10 over Barton River
June 26, 2017

## Slide 2: Introductions
Doug Bonneau, P.E.
VTrans Project Manager
David Peterson, P.E.
VTrans Project Engineer
Chris Mooney
VTrans Design Engineer
Geoff Dargan
VTrans Design Engineer

## Slide 3: Purpose of Meeting
Provide an understanding of our approach to the project
Provide an overview of project constraints
Discuss where we are at in the design process
Provide an opportunity to ask questions and voice concerns

## Slide 4
Project Location

## Slide 5: Meeting Overview
VTrans Project Development Process
Project Overview
  Existing Conditions
  Proposed Bridge
  New Layout of Intersection with parking and monument relocation
Maintenance of Traffic
Project Cost
Next Steps
Questions

## Slide 6: VTrans Project Development Process
Project Definition
Project Design
Construction
Project
Funded
Project
Defined
Contract
Award
Environmental permits
Develop plans, estimate and specifications
ROW process
Identify resources & constraints
Evaluate alternatives
Public participation
Build Consensus

## Slide 7: Project Overview
Existing Conditions
Proposed Bridge
Proposed Intersection Layout

## Slide 8: Description of Terms Used
Beams
(Superstructure)
Deck
Abutment
(Substructure)
Bridge Rail
Cross Section of Bridge

## Slide 9
Existing Conditions – Bridge #10
Roadway Classification – Rural Major Collector (Class 1 TH)
Bridge Type – 46’ Long Concrete T-Beam Bridge
Constructed in 1933
Ownership – Village of Orleans

## Slide 10: Existing Conditions – Bridge #10
The deck is in poor condition. There are areas of localized deterioration in the Concrete T-Beams
The horizontal curve is substandard
The existing vertical alignment through the project location does not meet the current standard
The bridge and approach railings do not meet current standard

## Slide 11
Existing Conditions - Bridge #10
Exposed reinforcing steel
At risk for full depth pop-outs
Bridge Deck

## Slide 12
Existing Conditions - Bridge #10
Settlement and stability issues
Leaching of fines
Retaining Wall Issues

## Slide 13: Design Criteria and Considerations
ADT of 4,900
DHV of 550
% Trucks: 3.0
Design Speed of 30 mph
Substandard Horizontal Alignment
Historic Bridge located in Orleans Village Historic District
Surrounding Section 4(f) resources

## Slide 14: Proposed Bridge #10
Full Replacement Off Alignment
  Replace the existing T-Beams with a new superstructure on a completely new substructure
  Construction will be phased – Maintain one lane traffic on half the existing bridge. Signalized for traffic in both directions
  Maintain existing width
  New bridge railing that compliments the Orleans Village Historic District
  Horizontal curve will be improved to meet standards and improve sight distance
  Utility relocation needed – Most of this work has already been completed
  ROW needed
  Construction will last for a full season (April – November)

## Slide 15: Proposed Typical Section
Proposed curb to curb = 32’

## Slide 16: Existing Memorial Park

## Slide 17: Proposed Memorial Park Layout

## Slide 18: Intersection Layout
Parking
Currently 15 marked parking spaces on Water and Maple Street
New parking layout will include 15 legally marked spaces.
Memorial
The existing memorial and park bench will be relocated to a new grassed area west of its current location
Creates a small park area where pedestrians will not need to cross the road to view the memorial

## Slide 19: Maintenance of Traffic Options
  Phased Construction
  Allows bridge to stay open during most of construction
  Longer construction duration
  Altered safety concerns
  Will require short closures of 2-3 weeks
Water Street to be closed to thru traffic at the intersection with VT 58 for duration of Phased Construction.
  Would require a fourth signal – increased cost and wait times at light.
  Provides space for contractor staging.

## Slide 20
Phased Construction
  One lane, alternating, with a traffic signal
  Existing is wide enough to complete deck replacement with 2 phases

## Slide 21: Phased Construction - Phase 1

## Slide 22: Phased Construction - Phase 2

## Slide 23: Project Cost
Preliminary Engineering | $385,000
ROW | $7,500
Construction w/ E & C | $2,900,000
Total | $3,292,500
Town Share is 5% will be approximately $164,625

## Slide 24
This is a list of a few important activities expected in the near future and is not a complete list of activities.
Develop Final Plans
Additional Subsurface Investigation (Borings)
Finalize Environmental Permits
Right-of-Way process
Next Steps – Bridge #10

## Slide 25: Orleans Village BF 0310(7) Questions & Comments VT Route 58 (Main Street/TH 1) – Bridge #10 over Barton River
June 26, 2017
For more information:
https://outside.vermont.gov/agency/vtrans/external/Projects/Structures/13J084