## Sheet1
| LUDLOW VILLAGE NH Deck (49) |  |  | Town-owned project |  |  | Bridge 26 over Jewell Brook
| GRS March 2019 |  |  | 18j009
District 3
| Key Parameters | [5 empty] | Windsor County
| Speed |  | 30 mph | by Village ordinance
| Functional Class |  | Principal Arterial, NHS |  |  | (Main St. Class 1, TH-1)
Extension of VT 103
Traffic Volumes
|  |  |  | 2023 | 2043
|  |  | AADT | 8800 | 9500
|  |  | DHV | 1100 | 1200
|  |  | ADTT | 850 | 1300
|  |  | %T | 7.1 | 10.2
|  |  | %D | 53 | 53
see Traffic Analysis memo for ESALs
| ROW | measured 3 rods on dgn in "work" folder of ROW file.
| Hydraulics |  | Bridge meets hydraulic standard for freeboard
Bank Full Width is unknown
Since town flooded during Irene, no lowering
of low beam allowed by hydraulics
| Inspection summary |  |  | deck rating: |  | 5
|  |  |  | super rating: |  | 7
|  |  |  | sub rating: |  | 6
Design Criteria
[5 empty] | Existing |  |  | VT State Std
| Lane and Shoulder |  |  |  | 11/12/12/11 |  |  | VSS says 10'-12' typical lane - assume 12' lanes, as
[5 empty] | w/5' sidewalk ea side |  |  | there is a lot of room here for large shoulders also.
2010 paving project (05B008) painted lines for
20' TW plus 4' S side, 12' TW plus 9' N side
Also, sidewalks on each side. Assume for now that
[5 empty] | deck fascia to fascia = 56.5' (Insp Report) |  |  | typical is 10.5/12/12/10.5 with two 5' sidewalks
[5 empty] | measured in top file: 56'-2" |  |  | Typical should be: 1.0' combination rail, 5' sidewalk
[5 empty] | record drawings: |  | 56'-0" | 0.5' curb, 9.5' shoulder, 12' lane, symmetrical, 1.5' OH
[5 empty] | from Route Log, typ width |  |  | Stripe as 4/8/12/12/8 plus sidewalks
is 24' travel way
| Clear Zone |  |  |  | Fascia is 28' away from centerline |  |  | 14' cut/16' fill
of roadway. Face of bridge railing
is 27'-1" from centerline of roadway.
If 12' lane is assumed, clear zone ends 11"
beyond face of rail. This could possibly
lead to small relocation of ornamental
light post(s). Doesn't look like there's
anything else closer to the roadway
than these posts.
Assume 16' clear zone, based on photos,
looks like a fill section.
| Banking |  |  |  | minimal banking
| Horizontal Alignment |  |  |  | Substantially straight |  |  | per AASHTO
| Vertical Grade | [6 empty] | 8% max. for urban level at 30 mph
| K Values |  |  |  | crest k= 11 |  |  | 30 crest
[5 empty] | sag k = 29 |  |  | 40 sag
Suggest not trying to correct
crest curve due to hydraulics
To raise the lower end is stretching
the scope out and affecting other
features that would also have to be raised.
Looking at Google Earth, K here is not a factor
Curve is also very short, visibility not a problem
| Skew |  |  |  | 20 degrees
| Vertical Clearance |  |  |  | NA
| Stopping Sight Distance |  |  |  | minimum HSD = 220' |  |  | 200'
| Bike/Ped | [6 empty] | 4' shared use shoulder req'd
| Existing Railing |  |  |  | substandard aluminum |  |  | crash-tested
| Load Rating/Capacity |  |  |  | Expect new Beams |  |  | HL-93
Utilities
Aerial utlities along south side of Main St.
Aerials also cross Main St. just east of the bridge - may need relocation (house service?)
Abandoned water line under bridge
active sewer line under bridge (in the stream bed) no impact
biological ID
* | Possible soil contamination in the area, probably no impact
We meet Hydraulics Std, no reduction in Low Beam
no Prime Ag soils
no wetlands
Maintain existing AOP and connectivity
* | Bats are the only RTE
cultural ID
Historic - bridge not historic, one historic property near,
some others eligible but none likely to be affected
no archaeological sensitivity
| Scope decisions | [7 empty] | X | check out Next Beam possibibilities
[9 empty] | X | check box girder possibilities for this project
1 | Deck is rated 5 and is showing signs of increasing deterioration, | [8 empty] | check sidewalk for loading during phase 1
| including delaminations seen from below, and increasing likelihood | [7 empty] | X | Prestressed slab super
| of full depth holes. Deck is 55 years old. REPLACE DECK | [8 empty] | determine radius of turn/geometry for splayed corner
[9 empty] | X | follow-up ROW - doesn't look right (water line)
2 | Superstructure is rated 7. They look pretty good in mid-span areas, | [8 empty] | review crash data
but there is some section loss nearer the bearings. Needs cleaning
and painting. Since this is a town project, and no opportunity to
| bundle painting project, painting would likely occur within this project. | [8 empty] | superstructure options
Existing beams are 18WFs with cover plates and shear studs according
| to record plans. | [8 empty] | solid slab - cast-in-place not feasible due to weight of reinforcing.
voided slab(?) - unlikely
| Arguments in support of retaining beams: | [8 empty] | beam/girder - varying spacings
Next Beams - looked at these, but unit width limits make it very difficult to construct
| They are rated 7 | [8 empty] | the width we want with phasing. Do not recommend Next Beams (plus they are more expensive)
keep total depths down to < 28"
| In the photos, they look pretty good; not a lot of section loss, except minor near bearings | [8 empty] | current overhangs are 1'-0" - check wider?
| With clean up and paint, they could probably go 60 years, after which abutments probably ready to go | [8 empty] | prestressed slabs are attractive possibility
Town project, more economical in the short term to retain supers for a while
Even without clean and paint, they can go 30 yr +
Arguments in support of replacing beams
Cleaning and painting in place is expensive - possible that the replacement is very competitive
Cover plates are square-ended, introducing some stress concentration, but they end in low moment regions.
It looks like there are shear studs on the existing beams, so probably faster, considering MOT, to replace beams
Paint on existing beams is almost certainly lead based, so hazardous procedures would be req'd - $$ & time
Supers are about 56 years old, according to shop dwgs dated 1964
JB is in favor of replacing supers - REPLACE SUPERSTRUCTURES
Consider a slab bridge; span is 45.25' brg-brg. This could work with a solid slab or voided slab. Current total depth of
structure is 6" slab, 2-3/4" min haunch, 18" beams, and 3/4" max. cover plates equalling a total of 27-7/8" max.
If PBUs are considered, assume they are not accelerated as phasing traffic is likely.
3 | Substructures are rated 6. They are scheduled to stay in place, some surface patching and crack filling
will be necessary. We believe subs were placed in 1931. We will consider cutting down the tops of the seats
to remove any compromised concrete, and to allow the new beams to be placed where we want them.
4 | Maintenance of Traffic - this project is wide enough to phase while keeping one lane of traffic open in each direction.
We should be able to get 23'-6" width min in each phase which should be sufficient. We will have to accommodate
pedestrians through the work zone.
5 | This is a rehab project, so Town's share is cut in half.
| Design Exceptions: |  | Crest curve - existing k value = 11 for crest on bridge, std is 30. See above
Approach Railing - no way we're going to meet standards here for approach railing on all corners
Probable clear zone violation by about 1', ornamental light posts - Town's decision.
6 | General: | Existing road surface is very slightly crowned according to review of the x-sections. Expect to blend in at
begin and end project. Maintain existing profile and slight crown. Drainage will be to the west on the west side of
the brook, flowing toward the CBs on north and south side of the road. East of the brook, drainage will continue to
CBs to the east. Looks like there might be a puddle on the SW side of the road at about station 118+75 or so. Hard
to tell, as it looks like some shoulder work was taking place at the time of the google photography - cold planing
on the shoulder.
Assumed Scope for initial Town discussions:
Replace superstructures and deck
Phase construction, maintaining two lanes in each direction at all times.
Standards not met - clear zone (light poles), K values, approach railings, probably hydraulics
Bikes will travel through work zone with vehicular traffic
Pedestrians: Pedestrians need a route through the work zone. Proposal is to funnel all to south side of Main St, via existing crosswalks,
then if westbound, along sidewalk on east side of Andover St. Then the route crosses Andover St. , staying in the Town ROW to the sidewalk on the south side of Main St.
Eastbound pedestrians do it in reverse. A temporary ped bridge would be needed probably south of the existing power pole on Andover St.
The existing ped bridge further down Andover St. is closed, likely due to its deteriorated condition.
Act 153: | The Town gets a 50% reduction in its share because this is a rehab project.
However, if the project is phased, the Town does not get a 50% reduction for not building temp bridge because the wording is, referring to the statement that says the Town share is 10%: "This section
does not apply to …. (section 26. 19VSA paragraph 309b. (6))…any project where, by mutual agreement of the municipality and agency, rehabilitation of an existing bridge
is the preferred alternative, in which case the agency shall use the appropriate combination of state and federal funding to pay either 95 percent of the cost of rehabilitation,
or 97.5 percent if the municipality closes the bridge and does not construct a temporary bridge for the duration of the project…..."
Therefore, the own's share is 5% of the total project costs for a phased project.
(If Town chooses a closure, Town Share is 2.5%)