## Slide 1: Reading ER P23-1(404) Selectboard Presentation VT 106 – Bridge #12 over North Branch Black River
September 9, 2024

## Slide 2: Introductions
Cory Burrall, P.E.
VTrans Structures Project Manager
Fianna Barrows, P.E.
VTrans Structures Lead Design Engineer
Jeff DeGraff, P.E.
VTrans Hydraulics Project Engineer

## Slide 3: Agenda
Provide an update to project development
Project overview and existing conditions
Hydraulic analysis
Proposed design and plans
Traffic management plan
Project schedule and timeline
Provide an opportunity to ask questions and voice any concerns

## Slide 4
Bridge 12
Project Location
Location Map

## Slide 5: Project Overview

## Slide 6
Bridge #12
Roadway Classification – Major Collector
Bridge Type – 52’ single span girders
Ownership – State of Vermont
Constructed in 1940
Looking North over Bridge

## Slide 7
Existing Conditions - Bridge #12
Deck Rating 6 (Satisfactory)
Superstructure Rating 6 (Satisfactory)
Substructure Rating 6 (Satisfactory)
24-month Inspection Frequency (from June 2023)

## Slide 8: Deck - Concrete
Spalling concrete in curbs and fascia
Exposed rebar

## Slide 9: Deck - Joints
Need to be repaired as potholes have started

## Slide 10: Superstructure – Steel Beams
Corrosion
Section loss

## Slide 11: Substructure - Abutment
Minor voids, missing stones, unsure of age of stone abutment

## Slide 12: Sediment and Slope: Steep & Flatter Slopes
Initial Slope
Original Bed
Bed Elevation before steepening

## Slide 13: Sediment and Bridges (Flat Slope)
Original Water Surface

## Slide 14: Sediment and Slope
Steep Slope
Flatter Slope

## Slide 15: Hydraulic Model
What is a hydraulic model?
  A physical or mathematical representation of a flow situation
What is used to develop a hydraulic model?
  Topographic Survey , LiDAR, Aerial Photograph
  Site Visit was performed to help determine failure modes and estimate roughness parameters
What was modeled?
  A 24-hour 100-year flood event was estimated with the use of a USDA Design Rainfall Event
  Existing Site and Bridge Conditions with a moveable bed and sediment load (Sediment Transport Model)
  Hypothetical Conditions – Raised the bridge and road by 5-ft with a bridge span of approximately 70-ft

## Slide 16: Existing Floodplain Extents
Falls
Bridge
Downstream Bend

## Slide 17: Existing Deposition
Falls
Bridge
Downstream Bend

## Slide 18
Bottom of Falls Location
Falls
10-ft of Deposition

## Slide 19
>40ft
Average upstream slope
1ft drop over 39 ft +/-
Bridge Location
Falls
Downstream Bend

## Slide 20: Design Criteria and Considerations
Criteria:
  Average Daily Traffic (ADT) - 2,056 vehicles per day
  Design Hourly Volume - 258 vehicles per hour
  % Trucks: 4.7%
  Design speed of 35 mph
  Vertical sight distance standards
  Bridge width standards
  Waterway clearance and hydraulic capacity
Considered:
  Right-of-Way needed; Utility relocation needed
  Adjacent property owners and drives
  Historically sensitive properties
  Nearby elementary school

## Slide 21
No Action
  Additional maintenance required within 10 years
Rehabilitation
  Repair any spalling concrete, replace missing stone in abutments, and replacement of joints
  New sidewalk/ curbs poured
  30-year design life
Superstructure Replacement
  New girders, bearings, deck, bridge rail, and bridge joints
  Would address the maintenance issues (curb spalling, poor joints)
  40-year design life
Full Bridge Replacement
  Maintain existing alignment
  75-year design life
Alternatives Considered

## Slide 22: Proposed Bridge Replacement – Bridge #12
Full Bridge Replacement
    New longer and shallower superstructure with concrete deck on galvanized steel beams
    Increased hydraulic capacity
    Widen Bridge to 11’/4’ typical each side to match corridor and provide bicycle/ pedestrian shoulder accommodations
      Currently 11’/4’ (with sidewalk) on only one side and 11’/0’ other side
    Meets all geometric criteria
      Increasing sight distance
      2% roadway crown and vertical curve to promote runoff
    Integral abutments with piles driven to bedrock
      Flood resiliency
    ROW needed; Minor utility relocation
    75-year design life
    Anticipated Construction – Summer 2026

## Slide 23: Recommended Design Alternative

## Slide 24: Proposed Typical Section

## Slide 25: Proposed Layout

## Slide 26: Proposed Profile

## Slide 27: Maintenance of Traffic Options Considered
Temporary Bridge
Phased Construction
Road Closure with Offsite Detour and Accelerated Bridge Construction Techniques to shorten duration

## Slide 28
Temporary Bridge
  Layout of One Lane Temporary Bridge on downstream side

## Slide 29
Phased Construction
  One lane traffic maintained per side
  Work Completed in 2-phases
  Tight proximity between traffic and workers
  Narrow bridge site
  Longest duration, highest cost

## Slide 30
Road Closure
  Detour: chosen and signed by State
  4-week closure (Bridge replacement option)
    While school out of session
    Alternating traffic control with flaggers outside closure period
  Innovations to reduce closure duration
    Prefabricated Bridge Units (PBU’s)
    Precast abutments
  Preferred Traffic Control Option
    Safest option to keep traffic away from construction area
    Shortest construction duration
    Least expensive option
    Longest life expectancy; less maintenance

## Slide 31: Traffic Control – Offsite Detour
  End to end: 32 minutes (23 miles)
  Through detour: 27 minutes (18 miles)
  VT 44 to VT 44A to US-5 to VT-131

## Slide 32: Project Schedule
Reading ER P23-1(404) Development Schedule | 
Scoping | Complete
Conceptual Plans | Complete
Preliminary Plans | Fall/Winter 2024
Permitting | Summer 2025
Final Plans | Summer 2025
Right-of-Way Clear | Fall 2025
Contract Plans | October 2025
Bid Advertisement | November 2025
Construction | April 2026 – October 2026 (Bridge closure 4 weeks during summer months while school out of session. Alternating one-way traffic with flaggers before and after closure period)

## Slide 33
For more information:
https://outside.vermont.gov/agency/vtrans/external/Projects/Structures/23b770
Reading ER P23-1(404) Questions and Comments VT 106 – Bridge #12 over North Branch Black River
September 9, 2024