## Project Planner
| Climate Action Office 2024 Engagement | [6 empty] | The engagement plan narrative includes descriptions of the Tactics.
| Select a week # to highlight. The week # is assigned to the month in which the Monday of that week falls. (Ex: The Monday of Week #5 is April 29, so it is assigned to April despite having more days in May.) | [5 empty] | Week # Highlight: | 13 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | COLLABORATORS | PLANNED START WEEK | PLANNED DURATION | ACTUAL START WEEK | ACTUAL DURATION | PERCENT COMPLETE | APRIL |  |  |  |  | MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61
Climate Action Plan Update | Plan & Promote 2 CAP Kickoff Public Meetings | CBI, VCC, CAO, JT Subcomm, other subcomms | 4 | 6 | 6 | 6 | 70%
| 2 CAP Kickoff Public Meetings | CBI, VCC, CAO, All Subcomms | 10 | 2 | 12 | 1 | 0%
| De-brief at July Subcommittee Meetings: What we heard at the CAP Kick-off events & how it will inform our work |  | 13 | 4
| Conversation (& presentation?) at September Subcommittee Meetings: results of on-the-ground engagement work & how it will inform our work |  | 23 | 4
| Plan 6 Stakeholder focus groups w/ drafting subcommittees (2 per subcomm). Invite people/groups who will be most impacted by the policies being considered. | CBI, VCC, CAO | 16 | 6 |  |  | 0%
| Host 6 Stakeholder focus groups w/ subcommittees. Focus on most impactful policies being considered. | CBI, VCC, CAO | 23 | 9 |  |  | 0%
| Municipal focus groups | RPCs, VCC, CAO | 23 | 9
| De-brief at October & November Subcommittee Meetings: What we heard at focus groups & how it will inform our work |  | 28 | 8
| 2 Public Meetings to share draft CAP | CBI, RPCs, VCC, CAO | 49 | 5 |  |  | 0%
| Ongoing Community-Based Engagement (Tactic #4) | CBI, VCC, CAO | 1 | 60 | 1 | 60 | 20%
| FY26: CAP is finalized & released (are we doing this WITH the RIS?) | CBI, RPCs, VCC, CAO |  |  |  |  | 0%
Resilience Implementation Strategy | Plan & Promote RIS Kickoff Public Meetings (Tactic #2) | CBI, Tre | 1 | 2 | 1 | 3 | 100%
| RIS Kickoff Public Meetings (Tactic #2) | CBI, Tre | 4 | 1 | 4 | 1 | 100%
| Post-kickoff survey |  | 5 | 1 | 5 | 1 | 100%
| Plan for Resilience Prior Public Engagement Assessment (Tactic #1) |  | 4 | 2 | 9 |  | 0%
| Climate Resilience Prior Public Engagement Assessment (Tactic #1) |  | 6 | 10 | 10 |  | 10%
| Ongoing Community-Based Engagement (Tactic #4) |  | 1 | 60 | 1 | 60 | 20%
| Tack on key RIS questions to CAP Stakeholder meetings (Tactic #3) |  | 23 | 9 |  |  | 0%
Ongoing Community Input Survey?
| Planning for Opportunity Assessment engagement (both public & stakeholder) |  | 36 | 4
| Opportunity Assessment Public Meetings (Tactic #2) |  | 41 | 8 |  |  | 0%
| Opportunity Assessment Stakeholder Workshops (Tactic #3) |  | 46 | 8 |  |  | 0%
| Cost Assessment Public Meetings (Tactic #2) | Treasurer's Office | 56 | 5 |  |  | 0%
| FY26: RIS is finalized & released (are we doing this WITH the CAP?) | Treasurer's Office, ANR Secretary (Cabinet?) |  |  |  |  | 0%
Note on AD4: Author: Milestone #1: Draft of Resilience Vision ready
Note on AN4: Author: Milestone #2: Final Resilience Vision ready