## Rural Resilience
Unique ID | #/ID | Sector/Subcommittee | PW CAP | Strategy CAP | Pathway | Strategies | Actions | Overall Priority Ranking | Lead Implementer (Post Legislative Action) | Co-Implementers / Key Stakeholders | ANR Department or Division | Action Status | Status Notes | Advancing and Being Implemented Actions that Need Further Resources (Y/N) | Implementor Has Statutory Authority for Action (Y/N) | Overall Priority for Advancement by State Government | Primary Action Type | Other Notes | CPRG Bin | Liz Miller Note | Liz Miller Note
50 | a | Rural Resilience and Adaptation | 18 | 18a | 18 Pathway 5: Ensure that all people have access to safe, accessible, energy efficient, and affordable housing. | 18a Update state and local land-use governance, regulations, practices, and investments to eliminate barriers to housing development. | Increase manufactured housing tax credits to replace older and inefficient manufactured homes. | High | Agency of Commerce and Community Development | Legislators, VHFA, VHCB, housing advocates |  | Being Implemented | The amount of available credits increased by $250,000 in the 2022 Legislative Session. | Yes | Yes | High | Resilience
51 | b | Rural Resilience and Adaptation | 18 | 18a | 18 Pathway 5: Ensure that all people have access to safe, accessible, energy efficient, and affordable housing. | 18a Update state and local land-use governance, regulations, practices, and investments to eliminate barriers to housing development. | Expand the existing program to relocate mobile home park homes and residents outside of flood vulnerable locations. | High | Vermont Emergency Management | Legislators, ACCD, VHCB, ANR |  | No Action Taken |  | Yes | Yes | High | Adaptation
52 | c | Rural Resilience and Adaptation | 18 | 18a | 18 Pathway 5: Ensure that all people have access to safe, accessible, energy efficient, and affordable housing. | 18a Update state and local land-use governance, regulations, practices, and investments to eliminate barriers to housing development. | Create a rental registry and inspection program to locate all of Vermont's rental housing and improve their quality and safety. | High | Agency of Commerce and Community Development | ADS, Rental Housing Advisory Board |  | No Action Taken | A proposal to create a rental registry was included in a 2023 legislative session omnibus housing bill, but was removed before a final housing bill passed. |  | No | Low | Resilience
53 | d | Rural Resilience and Adaptation | 18 | 18a | 18 Pathway 5: Ensure that all people have access to safe, accessible, energy efficient, and affordable housing. | 18a Update state and local land-use governance, regulations, practices, and investments to eliminate barriers to housing development. | Expand pilot program to train a network of local builders in the design and building of small and mid-sized and accessory dwelling units (mother-in-law apartments) and fund homes starts within communities planning and investing in development-ready infrastructure, building development partnerships, and updating zoning bylaws to welcome new homes. | High | Agency of Commerce and Community Development | Legislators, VHIP, Home Builders, DOL |  | Being Implemented | DHCD is working with consultants Utile of Boston on the Homes for All toolkit. The toolkit includes a missing middle homes design guide, VT-specific neighborhood infill case studies, a builders’ workbook, and training materials to jumpstart the creation of more affordable and accessible home types across VT, build a cohort of small scale developers, and grow local support for diverse housing options. |  | Yes | High | Resilience
54 | e | Rural Resilience and Adaptation | 18 | 18a | 18 Pathway 5: Ensure that all people have access to safe, accessible, energy efficient, and affordable housing. | 18a Update state and local land-use governance, regulations, practices, and investments to eliminate barriers to housing development. | Convene a statewide conversation on the Vermont Municipal and Regional Planning and Development Act’s (24 VSA, Chapter 117) provisions on land use and housing to outline amendments and strategies that will expand housing choice, opportunity, and improve community resilience. | High | Agency of Commerce and Community Development | Legislators, RPC, VHCB |  | Completed | DHCD engaged key stakeholders over the summer and fall of 2022 to develop proposed amendments to 24 VSA, Chapter 117 that would remove exclusionary zoning policies and make it easier to develop multiunit housing in areas served by water and wastewater. |  | No | High | Resilience
55 | a | Rural Resilience and Adaptation | 18 | 18b | 18 Pathway 5: Ensure that all people have access to safe, accessible, energy efficient, and affordable housing. | 18b Increase investments in the preservation and development of both private-market and nonprofit-owned affordable housing. | Continue to fund housing investments that leverage private initiative and funding to cost-effectively create housing units under models like the Re-Housing Recovery Program funding and the proposed Vermont Housing Investment Program. | High | Agency of Commerce and Community Development | Legislators, VHCB |  | Being Implemented | In 2022, the Legislature Authorized $20M in ARPA funds for the Vermont Housing Improvement Program. Between January 1st 2022 and June 30th 2023 the program has awarded ~$10M in grants to rehabilitate 244 vacant or blighted rental housing units. | Yes | Yes | High | Resilience
56 | b | Rural Resilience and Adaptation | 18 | 18b | 18 Pathway 5: Ensure that all people have access to safe, accessible, energy efficient, and affordable housing. | 18b Increase investments in the preservation and development of both private-market and nonprofit-owned affordable housing. | Create programs to assist prospective homebuyers to purchase and make improvements to homes that are energy inefficient and otherwise in need of immediate investment. | High | Agency of Commerce and Community Development | Legislators, PSD |  | Being Implemented | The network of non-profit housing development organizations and Homeownership Centers continue to receive ongoing operational support through Vermont Housing conservation Board grants as well as Community Development Block Grant funding to support ongoing efforts to improve organizational capacity for affordable housing development. Efforts are underway to utilize Vermont Housing Improvement Program funds to further increase staff capacity at these organizations. | Yes |  | High | Resilience
57 | c | Rural Resilience and Adaptation | 18 | 18b | 18 Pathway 5: Ensure that all people have access to safe, accessible, energy efficient, and affordable housing. | 18b Increase investments in the preservation and development of both private-market and nonprofit-owned affordable housing. | Increase support for mission-driven, non-profit housing developers to maintain their ability to produce high-quality, energy- and location-efficient housing. | High | Agency of Commerce and Community Development | Legislators, VHCB |  | Being Implemented |  |  |  | High | Resilience | awaiting input from Housing
58 | a | Rural Resilience and Adaptation | 18 | 18c | 18 Pathway 5: Ensure that all people have access to safe, accessible, energy efficient, and affordable housing. | 18c Increase access to fair and affordable housing for Vermonters who are housing instable. | Implement the recommendations of the Analysis of Impediments to Fair Housing. | High | Agency of Commerce and Community Development | ACCD, VHFA, RPC, VHCB |  | Being Implemented | Recommendations from the Analysis of Impediments to Fair Housing continue to be implemented. The Omnibus Housing Bill Act 182 and the Rental Safety Bill Act 181, both passed in 2022, and were significant in advancing the recommendations. An interim progress report provides more details on the status of recommendations. https://outside.vermont.gov/agency/ACCD/ACCD_Web_Docs/Housing/Fair-Housing/Analysis-of-Impediments/Condensed_AI_Update_2022.pdf. A more comprehensive update will be published in early 2024 | Yes |  | High | Resilience | Implementor has statutory authority to complete the analysis, but not necessarily to implement all recommendations from the analysis
59 | b | Rural Resilience and Adaptation | 18 | 18c | 18 Pathway 5: Ensure that all people have access to safe, accessible, energy efficient, and affordable housing. | 18c Increase access to fair and affordable housing for Vermonters who are housing instable. | Increase funding for community-based homelessness prevention and rapid re-housing. | High | Department of Children and Families | VHFA, ACCD |  | Advancing |  |  | Yes
60 | a | Rural Resilience and Adaptation | 14 | 14a | 14 Pathway 1: Increase capacity for climate resilience planning and implementation, and address inequities of under-resourced communities. | 14a Provide tools and resources to help communities assess climate vulnerabilities and create climate resilience plans. | Develop a climate planning toolkit to help towns assess vulnerabilities to climate change impacts, such as heat, air quality, drought, flooding, high winds, heavy rain, hail and sleet, and identify and prioritize actions to increase their resilience to climate change. Include newly developed tools, such as the vulnerability index, and existing tools, such as the AOT Repeat Flood Damage Inventory Tool, and the NOAA Climate Resilience Toolkit. | High | Agency of Natural Resources | RPCs | ANR - Climate Action Office | Being Implemented |  | Yes | Yes | High | Other | This Toolkit also includes mitigation components, so consider including in CPRG as mitigation co-benefit
66 | a | Rural Resilience and Adaptation | 14 | 14b | 14 Pathway 1: Increase capacity for climate resilience planning and implementation, and address inequities of under-resourced communities. | 14b Establish permanent statewide funding and technical support for local and regional climate resilience planning and project implementation to enhance rural resilience to impacts of climate change. | Increase funding to Regional Planning Commissions and local municipalities to support climate and energy planning and target funds to support towns with limited staff and marginalized populations that score high on the climate vulnerability index. | High | Agency of Natural Resources | ACCD, PSD | ANR - Climate Action Office | Advancing |  | Yes | Yes | High | Mitigation | Consider using leftover CPRG planning funds to build capacity for local climate and energy planning
67 | b | Rural Resilience and Adaptation | 14 | 14b | 14 Pathway 1: Increase capacity for climate resilience planning and implementation, and address inequities of under-resourced communities. | 14b Establish permanent statewide funding and technical support for local and regional climate resilience planning and project implementation to enhance rural resilience to impacts of climate change. | Create and fund one natural resource staff position at every Regional Planning Commissions to assist with implementation of climate policies and natural resources requirements such as Act 171 (forestry and habitat blocks). Use the Transportation Planning Initiative as a model to fund RPC natural resource staff and support trainings with ANR and other partners. | High | Agency of Natural Resources | ACCD, VEM, AOT | ANR - Climate Action Office | Advancing | Development of staff capacity via America the Beautiful grant | Yes | Yes | Medium | Sequestration |  | Other
68 | c | Rural Resilience and Adaptation | 14 | 14b | 14 Pathway 1: Increase capacity for climate resilience planning and implementation, and address inequities of under-resourced communities. | 14b Establish permanent statewide funding and technical support for local and regional climate resilience planning and project implementation to enhance rural resilience to impacts of climate change. | Increase and create a permanent state fund for design and implementation of local and regional climate adaptation and resilience projects. | High | Agency of Natural Resources | VEM, ACCD | ANR - Climate Action Office | No Action Taken |  |  | Yes | High | Adaptation
69 | d | Rural Resilience and Adaptation | 14 | 14b | 14 Pathway 1: Increase capacity for climate resilience planning and implementation, and address inequities of under-resourced communities. | 14b Establish permanent statewide funding and technical support for local and regional climate resilience planning and project implementation to enhance rural resilience to impacts of climate change. | Provide technical assistance to municipalities to assess the flood and erosion risks facing their drinking water and wastewater systems and identify potential mitigation improvements. | High | Agency of Natural Resources | DEC - Drinking Water and Groundwater Protection Division | DEC - Watershed Management Division | Advancing
70 | e | Rural Resilience and Adaptation | 14 | 14b | 14 Pathway 1: Increase capacity for climate resilience planning and implementation, and address inequities of under-resourced communities. | 14b Establish permanent statewide funding and technical support for local and regional climate resilience planning and project implementation to enhance rural resilience to impacts of climate change. | Establish a state level individual assistance program to provide financial assistance to uninsured or underinsured households impacted by disasters not federally declared. Program should incorporate Community Action Agencies and supporting networks to ensure assistance is received expeditiously by those that need it most. | Low | Agency of Human Services | Community Action Agencies, VEM |  | No Action Taken | Not in the budget; would need funding/capacity. |  | Yes
72 | a | Rural Resilience and Adaptation | 14 | 14c | 14 Pathway 1: Increase capacity for climate resilience planning and implementation, and address inequities of under-resourced communities. | 14c Expand cross-sector collaboration to align efforts, share best practices, and leverage resources to advance resilience and preparedness efforts statewide. | Identify and develop new programs to address the full range of climate impacts, especially those that impact important Vermont industries, including drought, less or irregular snowfall, and shorter or irregular sugaring season. | High | Agency of Natural Resources | VEM, VDH, ACCD, AOT, PSD, AAFM | ANR - Climate Action Office | Advancing |  | Yes | Yes | High | Adaptation
73 | b | Rural Resilience and Adaptation | 14 | 14c | 14 Pathway 1: Increase capacity for climate resilience planning and implementation, and address inequities of under-resourced communities. | 14c Expand cross-sector collaboration to align efforts, share best practices, and leverage resources to advance resilience and preparedness efforts statewide. | Complete a Statewide climate change impact assessment for Vermont’s commercial sector and natural resource based industries including but not limited to the ski, sugaring, and logging industries. | High | Agency of Commerce and Community Development | Agency of Natural Resources, DOL |  | No Action Taken | Seeking funding to support a climate vulnerability assessment and resiliency plan for the Tourism Industry. | Yes | No | High | Resilience
75 | a | Rural Resilience and Adaptation | 14 | 14d | 14 Pathway 1: Increase capacity for climate resilience planning and implementation, and address inequities of under-resourced communities. | 14d Increase community participation in local governance and support civic engagement and citizen involvement. | Require remote meeting options, including a call-in option for all meetings of public bodies; allow fully virtual meetings of public bodies with guidelines similar to the State of Emergencies; evaluate options for online collaboration in preparation for a meeting that can be done with transparency. | High | Secretary of State |  |  | Completed |  |  | Yes
19
77 | a | Rural Resilience and Adaptation | 15 | 15a | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15a Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience. | Develop a vulnerability index methodology and tool for broad use by stakeholders to identify priority areas for investment. The index will account for the vulnerability communication, energy, transportation, and water infrastructure in addition to socioeconomic and equity factors that affect community resilience. | High | Agency of Natural Resources | AOT, PSD, DEC | ANR - Climate Action Office | Being Implemented |  | No | Yes | High | Adaptation
78 | b | Rural Resilience and Adaptation | 15 | 15a | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15a Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience. | Update or adopt as appropriate infrastructure planning and design standards to reflect impacts from a changing climate, such as more frequent extreme weather as well as an increasing range of high and low temperatures, freeze/thaw cycles, and mixed precipitation (harden, incorporate redundancies, maximize life span, reduce annual maintenance and operational costs. etc.) | High | Department of Public Service | AOT, ANR, utilities, Vermont System Planning Committee, VCBB, NRB |  | No Action Taken | Not advancing in the way written, or by PSD. May need more discussion. | Yes | No | High | Adaptation | Adaptation and Resilience. This is a broad recommendation that goes beyond just electric grid infrastructure, to transportation, housing, etc. VEM should be added to implmenters/stakeholders, and perhaps ACCD, going to smart planning, land use development, etc. Natural REsources Board should be included. In the electric sector, PSD can be involved as it relates to engineering of infrastructure, which we review in siting proceedings.
79 | c | Rural Resilience and Adaptation | 15 | 15a | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15a Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience. | Seek federal stimulus (ARPA), infrastructure bill, and other non-ratepayer funding to defray costs of utility resilience upgrades that exceed benefits to ratepayers, such as: • Ubiquitous communications networks that enable full utilization and participation of distributed energy resources in an interactive grid. • Resilience Zones: batteries installed at or near critical facilities, potentially paired with solar (and/or small wind) and with a microgrid /islanding where possible, to allow them to continue to operate in the event of extended disruptions to electric service. • Strategic upgrades to substations, distribution, and transmission capacity across the Vermont grid needed to enable the state’s renewable and electrification goals, after first exploring feasibility of any lower-cost options, e.g. flexible load management, curtailment, and storage. • Emerging non-wires technologies that address major challenges system resilience (e.g. long-duration outages). | High | Department of Public Service | Utilities, BGS |  | Advancing | ARPA Funding secured: $7m for energy storage for customers and associated platforms to manage. Grid Resilience: $6m received and another $10m over 3 future years from DOE for utility investments that will reduce the duration and frequency of outages. Grid Resilience: $100m bid submitted to DOE by PSD for wide range of storage applications across utilities ARPA: ~$40m (?) for municipal resilience grants | Yes | Yes | High | Resilience | Resilience, but will also enable mitigation via electrification and creating capacity for distributed generation
80 | d | Rural Resilience and Adaptation | 15 | 15a | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15a Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience. | Create a framework for identifying and evaluating climate resilience threats and impacts to energy systems serving rural communities. | High | Department of Public Service | Utilities, VELCO |  | Action Modified - Advancing | PSD is drafting State Energy Assurance Plan - which in 2023 will identify a plan for creating an emergency action playbook, to be created in 2024 (Calendar Year). VEM added here, but perhaps should be the lead given Vulnerabilityi Index work for municipalities | Yes | Yes | High | Resilience | VEM should be added, this recommendation likely overlaps another dedicated to reslience…
81 | e | Rural Resilience and Adaptation | 15 | 15a | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15a Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience. | Complete the flood vulnerability assessment of all bridges, culverts and road segments on the state and town highway systems, identify and prioritize needed investments. This action includes completing the statewide expansion of the Transportation Resilience Planning Tool. | High | Agency of Transportation | ANR |  | Being Implemented | The Transportation Reslience Planning Tool (TRPT) is completed. It inlcudes both state and local highway systems. Prioritization of investemetns for state highways is being completed under the Resilience Improvement Plan. | Yes |  | High | Adaptation | VTrans has developed a Resilience Improvement Plan for state highway systems that results in prioritized locations for allocating IIJA PROTECT funding. The funding requires 2% be used for planning purposes.
82 | f | Rural Resilience and Adaptation | 15 | 15a | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15a Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience. | Complete a flood vulnerability assessment of state-owned rail infrastructure to identify and prioritize needed improvements. | High | Agency of Transportation | Railroad owners/operators |  | No Action Taken |  |  |  | Medium |  | Potential to expand TRPT to rail systems.
83 | g | Rural Resilience and Adaptation | 15 | 15a | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15a Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience. | Incorporate GHG reduction goals and CAP strategies, and actions related to resilience in the VTrans transportation planning and project development process. | High | Agency of Transportation | CAO |  | Being Implemented | VTrans is re-evaluating its existing Project Selection and Prioritization Sysytem to incorporate measures from the devlopment of the Carbon Reduction Strategy and Resilience Improvement Plan. | No | Yes | Medium
84 | h | Rural Resilience and Adaptation | 15 | 15a | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15a Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience. | Increase funding for floodplain restoration, including buy-out programs. | High | Vermont Emergency Management | ANR | DEC - Watershed Management Division | Advancing | Additional funding need following July 2023 flooding event and limited available ARPA funding remaining in the Flood Resilient Communities Fund. | Yes | Yes | High | Adaptation
85 | i | Rural Resilience and Adaptation | 15 | 15a | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15a Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience. | Increase investment to municipalities to support reductions in inflow and infiltration into wastewater collection systems. | High | Agency of Natural Resources |  | DEC - Water Investment Division | Action not defined | Clarity is needed as to what “increase” means: as compared to what? And by how much? |  | Yes
86 | j | Rural Resilience and Adaptation | 15 | 15a | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15a Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience. | Examine the climate impacts of sludge and biosolids to determine if regional facilities can reduce utility costs and climate impacts. Support investment in strategically placed facilities for sludge and septage processing (much is currently trucked to Montpelier/Chittenden Co.) | High | Agency of Natural Resources |  | DEC - Waste Management and Protection Division | Advancing | Sludge and septage get lumped together but the State is works on them somewhat separately. We have a state-wide septage management study that is nearing completion (4/30/24) and the state allocated pollution control funds directly for this project. Sludge, however, is still stuck in the ‘no action taken’ category. We have started internal discussions about sludge--part of why this is included in the CAP
87 | k | Rural Resilience and Adaptation | 15 | 15a | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15a Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience. | Increase efforts and funding towards pollution prevention programs at wastewater facilities to ensure that facilities protect available treatment capacity, which can focus development on already-served designated centers. | High | Agency of Natural Resources | Municipalities, DEC - Water Investment Division | DEC - Watershed Management Division | Being Implemented | Pollution prevention activities occur at pretreatment facilities. WSMD are currently managing ARPA pretreatment funds to support this work, but does not control or direct allocation of reserve capacity at wastewater treatment facilities. That the purview of the municipality. |  | Yes
88 | l | Rural Resilience and Adaptation | 15 | 15a | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15a Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience. | Understand source water vulnerabilities and invest in planning efforts to assist communities, especially those that are vulnerable for their long-term water supply needs. Revamp funding programs for source protection programs, increase funding for programs (include existing and new water sources) and conservation easements. | High | Agency of Natural Resources |  | DEC - Drinking Water and Groundwater Division | No Action Taken | we have a functional assessment of vulnerability, but nothing formal and basic regulations about sources in flood zones. Need updated vulnerability assessments to further this effort. | Yes | Yes | Medium | Resilience
89 | m | Rural Resilience and Adaptation | 15 | 15a | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15a Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience. | Increase the number of public water systems and publicly owned wastewater treatment works implementing an asset management program. Expanding programs, funding opportunities, and incentives to develop and implement these programs. | High | Agency of Natural Resources | DEC - Water Investment Division, Watershed Management Division | DEC - Drinking Water and Groundwater Division | Being Implemented | Existing part of the program which has increased but to apply state-wide need funding to support the effort/costs incurred. | Yes | Yes | High | Resilience
90 | n | Rural Resilience and Adaptation | 15 | 15a | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15a Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience. | Continue investments in traditional and green infrastructure to intercept, sink and treat stormwater. | High | Agency of Natural Resources |  | DEC - Water Investment Division | Being Implemented
91 | o | Rural Resilience and Adaptation | 15 | 15a | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15a Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience. | Encourage adoption of low impact development regulations for municipal zoning, including low water usage landscaping practices and increased density outside of flood prone areas. | High | Agency of Natural Resources |  | DEC - Water Investment Division | No Action Taken |  |  |  | Low
108 | a | Rural Resilience and Adaptation | 15 | 15b | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15b Public, private, and nonprofit entities should be prepared to respond and recover quickly to disruptions caused by severe weather and other climate change threats. | Strategically integrate planning and preparedness across disciplines and geographies addressing the interdependencies of transportation, energy, communications, and other systems. | High | Vermont Emergency Management | PSD, ANR, ACCD, VLECO, Broadband board/CUDs, municipalities |  | No Action Taken |  | No | Yes | High | Adaptation
111 | a | Rural Resilience and Adaptation | 15 | 15d | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15d Increase the resilience of critical infrastructure to severe weather and other climate change threats by reducing vulnerabilities of specific facilities. | Identify mission critical facilities in collaboration with local and regional planners, utilities and transportation providers to identify actions, procedures, or investments to mitigate the impact of extreme weather events to services provided by these facilities Examples of mission-critical facilities include designated emergency shelters, first responder facilities, hospitals and other medical facilities, key infrastructure such as water/wastewater pumping and treatment and sewer, key communications infrastructure such as fiber nodes, government offices, fuel suppliers, transportation hubs, supermarkets and other facilities municipalities identify as critical to serving communities during extreme weather events. | High | Vermont Emergency Management | PSD, ANR, AOT, RPCs, Municipalities |  | No Action Taken | Identified in the 2023 State Hazard Mitigation Plan as a need re: defining resilince hubs. | No | Yes | High | Adaptation |  |  | X | Questions that no action has been taken
112 | b | Rural Resilience and Adaptation | 15 | 15d | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15d Increase the resilience of critical infrastructure to severe weather and other climate change threats by reducing vulnerabilities of specific facilities. | Replace aging electric and communication infrastructure with the most appropriate resilient alternative when cost effective. For example, during normal replacement schedules for aging and unreliable lines, evaluate and where cost effective and feasible, improve resilience by relocating lines underground or through other options. | High | Department of Public Service | VELCO, Utilities |  | Advancing | Via Utility Integrated Resource Plans, and via investment decisions and infrastructure siting decisions. Some Grid Resilience funds may be available for assisting utiliteis, but more funding is needed | Yes | Yes | High | Resilience
113 | c | Rural Resilience and Adaptation | 15 | 15d | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15d Increase the resilience of critical infrastructure to severe weather and other climate change threats by reducing vulnerabilities of specific facilities. | Create a transportation flood resilience funding program to meet the requirements and related funding that are anticipated to be part of the 2021 reauthorization of the federal transportation act. | High | Agency of Transportation | VEM, ANR |  | Action Modified - Advancing | The 2021 IIJA created the PROTECT Prgoram for FFY '22 -'26 as well as a Discretionary Grant Program. | Yes | Yes | Medium | Adaptation | PROTECT Funds are being allocated to state system through priortiozation developed in the Resilience Improvement Plan. Planning funds will allow extension to other modes (i.e rail) as well as local systems. Will begin with a focus on allocating PROTECT funding and identifying projects for PROTECT grant applications. A long term fudning source, beyond IIJA, will be required.
114 | d | Rural Resilience and Adaptation | 15 | 15d | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15d Increase the resilience of critical infrastructure to severe weather and other climate change threats by reducing vulnerabilities of specific facilities. | Expand public investment, particularly hazard mitigation funding to flood-proof or relocate drinking water and wastewater treatment infrastructure at significant risk of flooding, when flood damaged, or during end-of-life refurbishment. |  | Agency of Natural Resources | VEM, DWGWPD, WSMD | DEC - Water Investment Division | Being Implemented
115 | e | Rural Resilience and Adaptation | 15 | 15d | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15d Increase the resilience of critical infrastructure to severe weather and other climate change threats by reducing vulnerabilities of specific facilities. | Work with Vermont villages and property owners to relocate septic systems and public or private drinking water wells that are at risk due to floods. |  | Agency of Natural Resources | VEM | DEC - Drinking Water and Groundwater Division | No Action Taken |  | Yes | No | Medium | Resilience
116 | f | Rural Resilience and Adaptation | 15 | 15d | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15d Increase the resilience of critical infrastructure to severe weather and other climate change threats by reducing vulnerabilities of specific facilities. | Develop programs to achieve net zero energy drinking water and wastewater treatment facilities Including microhydro, solar energy, heat exchange, building envelope; AND operational and technological efficiencies. |  | Agency of Natural Resources | EVT, PSD, WSMD | DEC - Drinking Water and Groundwater Division | No Action Taken | This is not part of our current program and will take a considerable effort to implement; analysis on feasibility needed. | Yes | No | Not Reviewed | Resilience
117 | g | Rural Resilience and Adaptation | 15 | 15d | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15d Increase the resilience of critical infrastructure to severe weather and other climate change threats by reducing vulnerabilities of specific facilities. | Improve road drainage around lakes / ponds to reduce stormwater runoff and erosion, especially on municipal roads. | High | Agency of Transportation | ANR |  | Action Modified - Being Implemented | ANR should be considered the lead on this through the MRGP. |  |  |  | Resilience | VTrans provides funding through state funded Better Roads, Grants in Aid Programs as well the federal funded Muncipal Highway Stormawater Mitigtion Programs. Other funding sources are also available to municipalities.
125 | a | Rural Resilience and Adaptation | 15 | 15d | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15d Increase the resilience of critical infrastructure to severe weather and other climate change threats by improving system efficiency, reliability and redundancies. | Evaluate the risks and opportunities created by potential climate change in-migration to VT's critical infrastructure. | High | Agency of Natural Resources | AOT, PSD, DEC | ANR - Climate Action Office | No Action Taken |  |  | Yes |  | Adaptation |  |  | X | Questions that no action taken: State Hazard Mitigation Plan?
126 | b | Rural Resilience and Adaptation | 15 | 15d | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15d Increase the resilience of critical infrastructure to severe weather and other climate change threats by improving system efficiency, reliability and redundancies. | Expand broadband to support remote work and tele-services to reduce the impact of travel disruptions. | High | Department of Public Service | VCBB |  | Advancing | The VCBB was established by Act 71 (2021)—An act relating to accelerated community broadband deployment—to coordinate, facilitate, support, and accelerate the development and implementation of universal community broadband solutions. The board will develop policies and programs to accelerate community efforts that advance the State’s goal of achieving universal access to reliable, high-quality, affordable, fixed broadband achieving speeds of at least 100 Mbps symmetrica |  | Yes | High | Other | https://publicservice.vermont.gov/vt-community-broadband-board-vcbb
127 | c | Rural Resilience and Adaptation | 15 | 15d | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15d Increase the resilience of critical infrastructure to severe weather and other climate change threats by improving system efficiency, reliability and redundancies. | Deploy foundational informational and operational technology statewide to enable and optimize storage and other distributed energy resources (e.g., GridLogic, Virtual Peaker, other emerging distributed energy resource management systems, in particular those that are open-source to various technologies and vendors) | High | Department of Public Service |  |  | Advancing | See lines 78/79 (unique ID in column B) | Yes | Yes | High | Resilience
128 | d | Rural Resilience and Adaptation | 15 | 15d | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15d Increase the resilience of critical infrastructure to severe weather and other climate change threats by improving system efficiency, reliability and redundancies. | Update the 1995 Vermont State Highway Design Standards to create context sensitive, multi-modal projects that support smart growth per the Act 167 (2014) Sec 26 Report - VT State Standards Work Plan. | High | Agency of Transportation | ACCD |  | Advancing | Selection of Consutlant pending review by committee. | Yes | Yes | High | Mitigation
129 | e | Rural Resilience and Adaptation | 15 | 15c | 15 Pathway 2: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide. | 15c Increase the resilience of critical infrastructure to severe weather and other climate change threats by improving system efficiency, reliability and redundancies. | Increase infrastructure investment needed to for walking, biking and transit; support planning for regional bike corridors to improve safety and transportation options between community centers. Identify and eliminate barriers to development, including inequities resulting from match, maintenance, and other requirements. | High | Agency of Transportation | Municipalities |  | Advancing | The Agency is implementing the Bicycle & Pedestrian Planning Integration Program working in partnership with the RPCs to map existing bicycle and pedestrian infrastructure, identify gaps, and incorporate improvements into highway asset management projects. | Yes | Yes | Medium | Mitigation | The Carbon Reduction Strategy includes modeling of differing investment strategies for bike, ped, and transit. | Transportation
132 | a | Rural Resilience and Adaptation | 16 | 16a | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16a Provide tools and resources to help assess data needs and establish best practices for rural communities, businesses, and institutions to reduce fossil fuel use. | Require the collection of fossil fuel usage data for municipal operations for buildings, vehicle fleets, and utilities; identify data gaps and ways to collect that data for measuring change in fossil fuel use going forward. | High | Agency of Natural Resources | PSD, AOT, BGS, RPCs | ANR - Climate Action Office | No Action Taken |  |  | No |  | Mitigation
133 | b | Rural Resilience and Adaptation | 16 | 16a | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16a Provide tools and resources to help assess data needs and establish best practices for rural communities, businesses, and institutions to reduce fossil fuel use. | Ensure data on fossil fuel usage at the municipal level is available and accessible in one location for municipal and public use. | High | Department of Public Service | AOT |  | No Action Taken | This data collection and sharing may be facilitated by the implementaion of the Clean Heat Standard, which requires that fuel sales be reported to the PUC. | No | Yes | Not Reviewed | Mitigation | Dept of Taxes, PUC, ANR should all be noted as co-implementers.
134 | c | Rural Resilience and Adaptation | 16 | 16a | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16a Provide tools and resources to help assess data needs and establish best practices for rural communities, businesses, and institutions to reduce fossil fuel use. | Engage higher education institutions to actively participate in developing systems to gather, compile, update, extrapolate fossil fuel data and make that available to the public. | High | University of Vermont | PSD, ANR, AOT |  | No Action Taken
135 | d | Rural Resilience and Adaptation | 16 | 16a | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16a Provide tools and resources to help assess data needs and establish best practices for rural communities, businesses, and institutions to reduce fossil fuel use. | Identify, develop, and share best practices for reducing municipal, school district, residential, commercial, and industrial fossil fuel consumption. Identify and assess existing practices and note gaps. | Medium | Department of Public Service | ANR | ANR - Climate Action Office | Advancing
137 | a | Rural Resilience and Adaptation | 16 | 16b | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16b Equitably expand access to programs that provide options to rural homeowners, landlords, municipalities, school districts, universities, and hospitals for weatherization, electrification, and utility upgrades. | Ensure that there is broad and statewide public education and promotion of benefits, economic and otherwise, and opportunities for fossil fuel reduction. | High | Department of Public Service | EVT, VEEP |  | Being Implemented | Significant educational efforts are occurring statewide. Entities include EEUs, DEV, VEEP, DUs |  |  |  | Mitigation
138 | b | Rural Resilience and Adaptation | 16 | 16b | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16b Equitably expand access to programs that provide options to rural homeowners, landlords, municipalities, school districts, universities, and hospitals for weatherization, electrification, and utility upgrades. | Evaluate all existing state-funded programs for effectiveness, access, and equity and consider increased funding for weatherization, energy efficiency and electrification programs in order to expand access to all Vermonters, and to expand programs with zero up-front costs. Existing programs may include Efficiency Vermont rebates, HEAT Squad - NeighborWorks of Western Vermont home energy audit program, and the Shared Equity program . In addition, the private sector should be engaged to provide innovative third-party financing opportunities that are paid for over time by the customer | High | Department of Public Service | DCF, EVT, HEAT Squad - NeighborWorks of Western Vermont home energy audit program, and the Shared Equity program |  | Advancing | EVT, DCF, and NWWVT have all received funding to invest in weatherization and electrfication. Act 174 provides $50 M to expand the State Energy Management Program to include Municipalites. | Yes | Yes | High | Mitigation | Additional funding could be infused into existing programs when ARPA funds are fully expended in 2026. The Department is supporting BGS' implementation of the Municipal Energy Resilience Program through additioanl DOE funding. | Buildings/Thermal
139 | c | Rural Resilience and Adaptation | 16 | 16b | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16b Equitably expand access to programs that provide options to rural homeowners, landlords, municipalities, school districts, universities, and hospitals for weatherization, electrification, and utility upgrades. | Explore Commercial PACE (Property Assessment Clean Energy) program for municipalities and other programs to elevate, such as bonding to support a statewide Tariffed On-Bill Finance Pilot and funding for a revolving loan fund for Public-Serving Institutions with retrofits. There may also be a need to continue providing the funding to support interest rate buydown (IRB) in EVT’s Home Energy Loan and Business Energy Loan programs. | High | Department of Public Service | EVT |  | No Action Taken | PACE efforts over the years have not taken off | No | No | Low | Mitigation |  |  | X | Questions no action taken: What about WRAP VHCA program?
140 | d | Rural Resilience and Adaptation | 16 | 16b | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16b Equitably expand access to programs that provide options to rural homeowners, landlords, municipalities, school districts, universities, and hospitals for weatherization, electrification, and utility upgrades. | Create new educational programs to increase public outreach for existing energy efficiency, electrification, and utility upgrade programs. | High | Agency of Education | PSD, VEEP, UVM
141 | e | Rural Resilience and Adaptation | 16 | 16b | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16b Equitably expand access to programs that provide options to rural homeowners, landlords, municipalities, school districts, universities, and hospitals for weatherization, electrification, and utility upgrades. | The Public Service Department should ensure that all utilities provide similar opportunities for all customers (rebates, incentives) to encourage fossil fuel reduction, electrification, and energy savings. | High | Department of Public Service | EVT |  | No Action Taken | The Department has not pushed utilities to offer similar rebates due to utility differences in cost structures and priorities. | No | No | Low | Mitigation |  |  | X | Questions no action taken: feels not right
142 | f | Rural Resilience and Adaptation | 16 | 16b | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16b Equitably expand access to programs that provide options to rural homeowners, landlords, municipalities, school districts, universities, and hospitals for weatherization, electrification, and utility upgrades. | Increase low-income weatherization through the State Weatherization Assistance Program including technical assistance to help households and landlords manage the process. | High | Department of Children and Families |  |  | Being Implemented | [7 empty] | X | Isn't some of this increase happening?
143 | g | Rural Resilience and Adaptation | 16 | 16b | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16b Equitably expand access to programs that provide options to rural homeowners, landlords, municipalities, school districts, universities, and hospitals for weatherization, electrification, and utility upgrades. | Entities that provide rebates for weatherization should stabilize rebate values year to year. | High | Department of Public Service | DCF, EVT |  | Action Modified - Advancing | The Deartment works with DUs and EEUs to avoid market disruption caused by changes in rebate amounts. Rebates have typically been increasing due to cost increases in labor and technologies. | No | Yes | Medium | Mitigation | The Department uses the regualtory process and its role as the State Energy Office receiving DOE funding to exert influence on rebate amounts. It may be appropriate to have varying amounts of incentives depending on the different market conditions at the time.
144 | h | Rural Resilience and Adaptation | 16 | 16b | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16b Equitably expand access to programs that provide options to rural homeowners, landlords, municipalities, school districts, universities, and hospitals for weatherization, electrification, and utility upgrades. | Expand workforce development programs such as the VT Training Program or the Department of Labor’s Workforce Education & Training Fund; cover costs for businesses to train in-house auditors/technicians. Pilot new programs in rural areas where workforce needed is greater. | High | Department of Labor |  |  | Action not defined | The strategies and the actions don't align. VDOL programs are focused on occupational training - so some part of the action "cover costs for businesses to train in-house auditors/technicians" does make sense for VDOL - it's in the realm of apprenticeship, but we could also promote our programs differently to attract people interested in climate action. We still need to address where workers are coming from. There is a state-wide shortage of available talent.
145 | i | Rural Resilience and Adaptation | 16 | 16b | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16b Equitably expand access to programs that provide options to rural homeowners, landlords, municipalities, school districts, universities, and hospitals for weatherization, electrification, and utility upgrades. | Revise state building energy codes and standards to require a minimum 200 Amp service for new construction as electrification expands. | High | Department of Public Service |  |  | Completed | This is included in the most recent Energy Code Update | No | Yes | Medium | Mitigation | Updated Code to take effect in June 2023
146 | j | Rural Resilience and Adaptation | 16 | 16b | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16b Equitably expand access to programs that provide options to rural homeowners, landlords, municipalities, school districts, universities, and hospitals for weatherization, electrification, and utility upgrades. | Provide funding to assist low-income homeowners to upgrade electric service to 200 Amps. Electric utilities and renewable energy developers could provide new incentives and financing options through third-party financing mechanisms, on bill financing, RES Tier III incentives , third-party power purchase agreements, and grants. All programs must include equal access to renters. | High | Department of Public Service | EVT |  | Advancing | $20 M in ARPA funding for residential panel upgrades is being granted to Efficiency Vermont | Yes | Yes | High | Mitigation | Funding is expected to reach up to 4,000 low and moderate income households. Significantly more funding will be necessary to meet the roughly 100,000 Vermont households requiring upgrades to 200 amp service. | Buildings/Thermal
147 | k | Rural Resilience and Adaptation | 16 | 16b | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16b Equitably expand access to programs that provide options to rural homeowners, landlords, municipalities, school districts, universities, and hospitals for weatherization, electrification, and utility upgrades. | Implement a statewide program to support electrification of municipal fleet vehicles ensuring it is designed to allow equitable access and participation to municipalities regardless of tax base. | High | Agency of Transportation | EVT, CSE |  | Advancing | Electrify Your Fleet program in development | No | Yes | High | Mitigation | AOT is working to design the program in-house and launch as a grant program. | Transportation
148 | l | Rural Resilience and Adaptation | 16 | 16b | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16b Equitably expand access to programs that provide options to rural homeowners, landlords, municipalities, school districts, universities, and hospitals for weatherization, electrification, and utility upgrades. | Support water and wastewater systems in conducting and implementing energy audits and recommendations for energy reduction and electrification. | High | Agency of Natural Resources | PSD, EVT, WSMD | DEC - Water Investment Division |  |  | Yes | Yes | Medium | Mitigation | Entry completed by CAO | Other
149 | m | Rural Resilience and Adaptation | 16 | 16b | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16b Equitably expand access to programs that provide options to rural homeowners, landlords, municipalities, school districts, universities, and hospitals for weatherization, electrification, and utility upgrades. | Develop cost-effective programs to support renewable energy development on school and other municipal property and evaluate and eliminate unnecessary statutory barriers related to capital financing and land purchase/lease. | High | Department of Public Service | EVT, ACCD, AOE, PUC, VHFA |  | Action Modified - Advancing | PSD has undertaken robust public engagement to learn more about Vters preferences for electric supply resources and design of Renewable Energy standards and supporting programs such as net metering. Further, PSD has developed Affordable Community Renewable Energy program to support low income customers receiving the benefit of local renewable energy. The PSD received $1m CDS from DOE, following on ARPA $ for School RE program, supporting wood chip boilers for schools, primarily, but also EE investments. Finally, the Department is responding to EPA's "solar for all" competition with $100m proposal that would further provide support for LI solar. Evaluation of barriers to land use/leasing and capital financing has not been started | Yes | Yes | Medium | Mitigation | EVT has no role here and should be deleted from the co-implementer/stakeholder list. VEIC may particiapte.
150 | n | Rural Resilience and Adaptation | 16 | 16b | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16b Equitably expand access to programs that provide options to rural homeowners, landlords, municipalities, school districts, universities, and hospitals for weatherization, electrification, and utility upgrades. | Help individuals, municipalities, and businesses through the process of weatherization, energy efficiency and fuel switching upgrades by establishing and funding Weatherization and Efficiency Navigators at each Regional Planning Commission (RPC), expanding the services currently available at CAA agencies and VEIC, and ensuring coordination and a whole systems approach among the entities providing services. | High | Agency of Natural Resources | PUC, EVT, RPC, VEIC, CAA, ACCD | ANR - Climate Action Office | No Action Taken |  |  | Yes | High | Mitigation |  | Buildings/Thermal
151 | o | Rural Resilience and Adaptation | 16 | 16b | 16 Pathway 3: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. | 16b Equitably expand access to programs that provide options to rural homeowners, landlords, municipalities, school districts, universities, and hospitals for weatherization, electrification, and utility upgrades. | Review and expand existing programs to support landlords in weatherizing rental properties, including St. Johnsbury Rental Housing Improvement Program, and other programs in counties and towns. | High | Department of Public Service | DCF, EVT |  | Action Modified - Advancing | PSD is subgranting ARPA funds to Efficiency VT for weatherization and flood relief, there are robust incentives for landlords in these funds. |  |  |  | Resilience | ACCD not lead implementer
165 | a | Rural Resilience and Adaptation | 17 | 17a | 17 Pathway 4: Change Vermont's land-use policies so current and future land development will be adaptive and resilient to climate change impacts. | 17a Increase investment in the infrastructure (sewer, water, stormwater, sidewalks, bike lanes, EV charging, broadband, energy supply) needed to support communities that are more resilient to climate disruptions, equitable, resource efficient, and protects the adaptive capacity of natural resources. | Monitor and update stormwater permitting process as needed to ensure green infrastructure is preferred in design considerations. | High | Agency of Natural Resources | RPCs, Municipalities | DEC - Watershed Management Division | Being Implemented | Revision of the Vermont Stormwater Managment Manual is underway in 2023, with expected completion in 2024. The manual framework emphasizes distributed runoff reduction practices over centralized grey infrastructure practices | No | Yes | High | Mitigation | The manual is reviewed and revised (if necessary) every 5 years, as established in Rule. This will be an ongoing effort regardless of the CAP.
166 | b | Rural Resilience and Adaptation | 17 | 17a | 17 Pathway 4: Change Vermont's land-use policies so current and future land development will be adaptive and resilient to climate change impacts. | 17a Increase investment in the infrastructure (sewer, water, stormwater, sidewalks, bike lanes, EV charging, broadband, energy supply) needed to support communities that are more resilient to climate disruptions, equitable, resource efficient, and protects the adaptive capacity of natural resources. | Increase investment in stormwater and green infrastructure, including separating combined wastewater and storm water systems, to protect public health and water quality. | High | Agency of Natural Resources | WID | DEC - Watershed Management Division | Being Implemented | Control of funding is with WID. WSMD has a Combined Sewer Overflow Rule that requires Long-Term to Control Plans that will lead to separation of combined systems.
167 | c | Rural Resilience and Adaptation | 17 | 17a | 17 Pathway 4: Change Vermont's land-use policies so current and future land development will be adaptive and resilient to climate change impacts. | 17a Increase investment in the infrastructure (sewer, water, stormwater, sidewalks, bike lanes, EV charging, broadband, energy supply) needed to support communities that are more resilient to climate disruptions, equitable, resource efficient, and protects the adaptive capacity of natural resources. | Complete a Climate Readiness assessments of drinking water, stormwater, and wastewater infrastructure. (This is an EPA tool that looks at all climate impacts including, fires, droughts, flooding, etc.). | High | Agency of Natural Resources | WSMD | DEC - Drinking Water and Groundwater Division | No Action Taken | Needing vulnerability assessment to ID where to allocate resources before commencing. Certain aspects are intrinsic in the program, but not the entire approach. | No | No | Medium | Resilience
168 | d | Rural Resilience and Adaptation | 17 | 17a | 17 Pathway 4: Change Vermont's land-use policies so current and future land development will be adaptive and resilient to climate change impacts. | 17a Increase investment in the infrastructure (sewer, water, stormwater, sidewalks, bike lanes, EV charging, broadband, energy supply) needed to support communities that are more resilient to climate disruptions, equitable, resource efficient, and protects the adaptive capacity of natural resources. | Examine regionalization efforts and sharing of resources for all water utilities. | High | Agency of Natural Resources | WSMD | DEC - Drinking Water and Groundwater Division | No Action Taken | If we are only examining resources, this can be done; if there is implementation we would need funding and stautory authority. | No | No | Medium | Resilience
169 | e | Rural Resilience and Adaptation | 17 | 17a | 17 Pathway 4: Change Vermont's land-use policies so current and future land development will be adaptive and resilient to climate change impacts. | 17a Increase investment in the infrastructure (sewer, water, stormwater, sidewalks, bike lanes, EV charging, broadband, energy supply) needed to support communities that are more resilient to climate disruptions, equitable, resource efficient, and protects the adaptive capacity of natural resources. | Invest in enhancing water sources in vulnerable communities to enhance resilience to long-term drought. | High | Agency of Natural Resources | VLCT, RPC | DEC - Drinking Water and Groundwater Division | Advancing | Consideration of drought effects intrinsic in current program for new permits, need additional resources to assist those that pre-date the permitting program or have been demonstrated to be vulnerable. | Yes | No | High | Resilience
170 | f | Rural Resilience and Adaptation | 17 | 17a | 17 Pathway 4: Change Vermont's land-use policies so current and future land development will be adaptive and resilient to climate change impacts. | 17a Increase investment in the infrastructure (sewer, water, stormwater, sidewalks, bike lanes, EV charging, broadband, energy supply) needed to support communities that are more resilient to climate disruptions, equitable, resource efficient, and protects the adaptive capacity of natural resources. | Increase investment to municipalities for new and expanded water and wastewater facilities to support reductions in inflow and infiltration into wastewater collection systems. | High | Agency of Natural Resources | VLCT, VNRC, RPC, ACCD, WSMD, WID | DEC - Drinking Water and Groundwater Division | Advancing | Clarity needed re: what kind of reductions; we currently implement and follow existing design calculations and/or plumbing code for drinking water flows. | Yes | No | Low | Resilience
177 | a | Rural Resilience and Adaptation | 17 | 17b | 17 Pathway 4: Change Vermont's land-use policies so current and future land development will be adaptive and resilient to climate change impacts. | 17b Develop permanent private and public funding sources to flood-proof, elevate and purchase commercial and residential properties, as well as conserve and restore ecosystem services upstream to protect our people, property, environment, and economy from flooding. | Establish a dedicated, comprehensive state level program with funding to strategically purchase or match funding for hazard-prone properties, easements to conserve river corridors, floodplains, forests, and wetlands to reduce overall flood risk and enhance flood storage statewide. | High | Vermont Emergency Management | ANR, ACCD, WID |  | Advancing | Advancing in legislature. Also, The Rivers Program currently administers a River Corridor Easement Program, with WID providing the funding from the Clean Water Fund. To expand this program as "comprehensive state program" is beyond WSMD capacity and would require broader Agency support.
178 | b | Rural Resilience and Adaptation | 17 | 17b | 17 Pathway 4: Change Vermont's land-use policies so current and future land development will be adaptive and resilient to climate change impacts. | 17b Develop permanent private and public funding sources to flood-proof, elevate and purchase commercial and residential properties, as well as conserve and restore ecosystem services upstream to protect our people, property, environment, and economy from flooding. | Expand the eligibility criteria and increase funding for VHCB's conservation and buyout program, to address any flood-vulnerable structures. | Low | Vermont Housing and Conservation Board | ANR, VEM |  | No Action Taken | VHCB had developed and implemented a flood buyout program following Tropical Storme Irene, but that has not been refunded in response to the flooding last summer. We are making other flood resilience and recovery investments, but not as this action frames the work. If we are directed to do so, we could revisit this.
179 | c | Rural Resilience and Adaptation | 17 | 17b | 17 Pathway 4: Change Vermont's land-use policies so current and future land development will be adaptive and resilient to climate change impacts. | 17b Develop permanent private and public funding sources to flood-proof, elevate and purchase commercial and residential properties, as well as conserve and restore ecosystem services upstream to protect our people, property, environment, and economy from flooding. | Fund ERAF for non-federal disasters in towns that have adopted floodplain and/or river corridor bylaws and to support the 25% non-federal match for buyouts and develop criteria for distribution when funding is limited. | Low | Vermont Emergency Management | ANR |  | No Action Taken |  | No | No | Low | Adaptation

## RR Simplified All
Actions | Status
Pathway 14: Increase capacity for climate resilience planning and implementation, and address inequities of under-resourced communities.
Strategy 14a: Provide tools and resources to help communities assess climate vulnerabilities and create climate resilience plans.
Develop a climate planning toolkit to help towns assess vulnerabilities to climate change impacts, such as heat, air quality, drought, flooding, high winds, heavy rain, hail and sleet, and identify and prioritize actions to increase their resilience to climate change. Include newly developed tools, such as the vulnerability index, and existing tools, such as the AOT Repeat Flood Damage Inventory Tool, and the NOAA Climate Resilience Toolkit. | Being Implemented
Strategy 14b: Establish permanent statewide funding and technical support for local and regional climate resilience planning and project implementation to enhance rural resilience to impacts of climate change.
Create and fund one natural resource staff position at every Regional Planning Commissions to assist with implementation of climate policies and natural resources requirements such as Act 171 (forestry and habitat blocks). Use the Transportation Planning Initiative as a model to fund RPC natural resource staff and support trainings with ANR and other partners. | Advancing
Provide technical assistance to municipalities to assess the flood and erosion risks facing their drinking water and wastewater systems and identify potential mitigation improvements. | Advancing
Increase funding to Regional Planning Commissions and local municipalities to support climate and energy planning and target funds to support towns with limited staff and marginalized populations that score high on the climate vulnerability index. | Advancing
Increase and create a permanent state fund for design and implementation of local and regional climate adaptation and resilience projects. | No Action Taken
Establish a state level individual assistance program to provide financial assistance to uninsured or underinsured households impacted by disasters not federally declared. Program should incorporate Community Action Agencies and supporting networks to ensure assistance is received expeditiously by those that need it most. | No Action Taken
Strategy 14c: Expand cross-sector collaboration to align efforts, share best practices, and leverage resources to advance resilience and preparedness efforts statewide.
Identify and develop new programs to address the full range of climate impacts, especially those that impact important Vermont industries, including drought, less or irregular snowfall, and shorter or irregular sugaring season. | Advancing
Complete a Statewide climate change impact assessment for Vermont’s commercial sector and natural resource based industries including but not limited to the ski, sugaring, and logging industries. | No Action Taken
Strategy 14d: Increase community participation in local governance and support civic engagement and citizen involvement.
Require remote meeting options, including a call-in option for all meetings of public bodies; allow fully virtual meetings of public bodies with guidelines similar to the State of Emergencies; evaluate options for online collaboration in preparation for a meeting that can be done with transparency. | Completed
Pathway 15: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide.
Strategy 15a: Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience.
Create a framework for identifying and evaluating climate resilience threats and impacts to energy systems serving rural communities. | Advancing (Action Modified)
Increase funding for floodplain restoration, including buy-out programs. | Advancing
Seek federal stimulus (ARPA), infrastructure bill, and other non-ratepayer funding to defray costs of utility resilience upgrades that exceed benefits to ratepayers, such as: • Ubiquitous communications networks that enable full utilization and participation of distributed energy resources in an interactive grid. • Resilience Zones: batteries installed at or near critical facilities, potentially paired with solar (and/or small wind) and with a microgrid /islanding where possible, to allow them to continue to operate in the event of extended disruptions to electric service. • Strategic upgrades to substations, distribution, and transmission capacity across the Vermont grid needed to enable the state’s renewable and electrification goals, after first exploring feasibility of any lower-cost options, e.g. flexible load management, curtailment, and storage. • Emerging non-wires technologies that address major challenges system resilience (e.g. long-duration outages). | Advancing
Complete the flood vulnerability assessment of all bridges, culverts and road segments on the state and town highway systems, identify and prioritize needed investments. This action includes completing the statewide expansion of the Transportation Resilience Planning Tool. | Being Implemented
Develop a vulnerability index methodology and tool for broad use by stakeholders to identify priority areas for investment. The index will account for the vulnerability communication, energy, transportation, and water infrastructure in addition to socioeconomic and equity factors that affect community resilience. | Being Implemented
Increase the number of public water systems and publicly owned wastewater treatment works implementing an asset management program. Expanding programs, funding opportunities, and incentives to develop and implement these programs. | Being Implemented
Incorporate GHG reduction goals and CAP strategies, and actions related to resilience in the VTrans transportation planning and project development process. | Being Implemented
Update or adopt as appropriate infrastructure planning and design standards to reflect impacts from a changing climate, such as more frequent extreme weather as well as an increasing range of high and low temperatures, freeze/thaw cycles, and mixed precipitation (harden, incorporate redundancies, maximize life span, reduce annual maintenance and operational costs. etc.) | No Action Taken
Understand source water vulnerabilities and invest in planning efforts to assist communities, especially those that are vulnerable for their long-term water supply needs. Revamp funding programs for source protection programs, increase funding for programs (include existing and new water sources) and conservation easements. | No Action Taken
Complete a flood vulnerability assessment of state-owned rail infrastructure to identify and prioritize needed improvements. | No Action Taken
Encourage adoption of low impact development regulations for municipal zoning, including low water usage landscaping practices and increased density outside of flood prone areas. | No Action Taken
Increase investment to municipalities to support reductions in inflow and infiltration into wastewater collection systems. | Action not defined
Examine the climate impacts of sludge and biosolids to determine if regional facilities can reduce utility costs and climate impacts. Support investment in strategically placed facilities for sludge and septage processing (much is currently trucked to Montpelier/Chittenden Co.) | Advancing
Increase efforts and funding towards pollution prevention programs at wastewater facilities to ensure that facilities protect available treatment capacity, which can focus development on already-served designated centers. | Being Implemented
Continue investments in traditional and green infrastructure to intercept, sink and treat stormwater. | Being Implemented
Strategy 15b: Public, private, and nonprofit entities should be prepared to respond and recover quickly to disruptions caused by severe weather and other climate change threats.
Strategically integrate planning and preparedness across disciplines and geographies addressing the interdependencies of transportation, energy, communications, and other systems. | No Action Taken
Strategy 15c: Increase the resilience of critical infrastructure to severe weather and other climate change threats by reducing vulnerabilities of specific facilities.
Increase infrastructure investment needed to for walking, biking and transit; support planning for regional bike corridors to improve safety and transportation options between community centers. Identify and eliminate barriers to development, including inequities resulting from match, maintenance, and other requirements. | Advancing
Strategy 15d: Increase the resilience of critical infrastructure to severe weather and other climate change threats by improving system efficiency, reliability and redundancies.
Deploy foundational informational and operational technology statewide to enable and optimize storage and other distributed energy resources (e.g., GridLogic, Virtual Peaker, other emerging distributed energy resource management systems, in particular those that are open-source to various technologies and vendors) | Advancing
Expand broadband to support remote work and tele-services to reduce the impact of travel disruptions. | Advancing
Update the 1995 Vermont State Highway Design Standards to create context sensitive, multi-modal projects that support smart growth per the Act 167 (2014) Sec 26 Report - VT State Standards Work Plan. | Advancing
Evaluate the risks and opportunities created by potential climate change in-migration to VT's critical infrastructure. | No Action Taken
Create a transportation flood resilience funding program to meet the requirements and related funding that are anticipated to be part of the 2021 reauthorization of the federal transportation act. | Advancing (Action Modified)
Improve road drainage around lakes / ponds to reduce stormwater runoff and erosion, especially on municipal roads. | Being Implemented (Action Modified)
Replace aging electric and communication infrastructure with the most appropriate resilient alternative when cost effective. For example, during normal replacement schedules for aging and unreliable lines, evaluate and where cost effective and feasible, improve resilience by relocating lines underground or through other options. | Advancing
Identify mission critical facilities in collaboration with local and regional planners, utilities and transportation providers to identify actions, procedures, or investments to mitigate the impact of extreme weather events to services provided by these facilities Examples of mission-critical facilities include designated emergency shelters, first responder facilities, hospitals and other medical facilities, key infrastructure such as water/wastewater pumping and treatment and sewer, key communications infrastructure such as fiber nodes, government offices, fuel suppliers, transportation hubs, supermarkets and other facilities municipalities identify as critical to serving communities during extreme weather events. | No Action Taken
Work with Vermont villages and property owners to relocate septic systems and public or private drinking water wells that are at risk due to floods. | No Action Taken
Develop programs to achieve net zero energy drinking water and wastewater treatment facilities Including microhydro, solar energy, heat exchange, building envelope; AND operational and technological efficiencies. | No Action Taken
Expand public investment, particularly hazard mitigation funding to flood-proof or relocate drinking water and wastewater treatment infrastructure at significant risk of flooding, when flood damaged, or during end-of-life refurbishment. | Being Implemented
Pathway 16: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities.
Strategy 16a: Provide tools and resources to help assess data needs and establish best practices for rural communities, businesses, and institutions to reduce fossil fuel use.
Ensure data on fossil fuel usage at the municipal level is available and accessible in one location for municipal and public use. | No Action Taken
Require the collection of fossil fuel usage data for municipal operations for buildings, vehicle fleets, and utilities; identify data gaps and ways to collect that data for measuring change in fossil fuel use going forward. | No Action Taken
Identify, develop, and share best practices for reducing municipal, school district, residential, commercial, and industrial fossil fuel consumption. Identify and assess existing practices and note gaps. | Advancing
Engage higher education institutions to actively participate in developing systems to gather, compile, update, extrapolate fossil fuel data and make that available to the public. | No Action Taken
Strategy 16b: Equitably expand access to programs that provide options to rural homeowners, landlords, municipalities, school districts, universities, and hospitals for weatherization, electrification, and utility upgrades.
Develop cost-effective programs to support renewable energy development on school and other municipal property and evaluate and eliminate unnecessary statutory barriers related to capital financing and land purchase/lease. | Advancing (Action Modified)
Entities that provide rebates for weatherization should stabilize rebate values year to year. | Advancing (Action Modified)
Evaluate all existing state-funded programs for effectiveness, access, and equity and consider increased funding for weatherization, energy efficiency and electrification programs in order to expand access to all Vermonters, and to expand programs with zero up-front costs. Existing programs may include Efficiency Vermont rebates, HEAT Squad - NeighborWorks of Western Vermont home energy audit program, and the Shared Equity program . In addition, the private sector should be engaged to provide innovative third-party financing opportunities that are paid for over time by the customer | Advancing
Provide funding to assist low-income homeowners to upgrade electric service to 200 Amps. Electric utilities and renewable energy developers could provide new incentives and financing options through third-party financing mechanisms, on bill financing, RES Tier III incentives , third-party power purchase agreements, and grants. All programs must include equal access to renters. | Advancing
Implement a statewide program to support electrification of municipal fleet vehicles ensuring it is designed to allow equitable access and participation to municipalities regardless of tax base. | Advancing
Ensure that there is broad and statewide public education and promotion of benefits, economic and otherwise, and opportunities for fossil fuel reduction. | Being Implemented
Revise state building energy codes and standards to require a minimum 200 Amp service for new construction as electrification expands. | Completed
Help individuals, municipalities, and businesses through the process of weatherization, energy efficiency and fuel switching upgrades by establishing and funding Weatherization and Efficiency Navigators at each Regional Planning Commission (RPC), expanding the services currently available at CAA agencies and VEIC, and ensuring coordination and a whole systems approach among the entities providing services. | No Action Taken
Explore Commercial PACE (Property Assessment Clean Energy) program for municipalities and other programs to elevate, such as bonding to support a statewide Tariffed On-Bill Finance Pilot and funding for a revolving loan fund for Public-Serving Institutions with retrofits. There may also be a need to continue providing the funding to support interest rate buydown (IRB) in EVT’s Home Energy Loan and Business Energy Loan programs. | No Action Taken
The Public Service Department should ensure that all utilities provide similar opportunities for all customers (rebates, incentives) to encourage fossil fuel reduction, electrification, and energy savings. | No Action Taken
Support water and wastewater systems in conducting and implementing energy audits and recommendations for energy reduction and electrification. | More Information Needed
Create new educational programs to increase public outreach for existing energy efficiency, electrification, and utility upgrade programs. | More Information Needed
Review and expand existing programs to support landlords in weatherizing rental properties, including St. Johnsbury Rental Housing Improvement Program, and other programs in counties and towns. | Advancing (Action Modified)
Increase low-income weatherization through the State Weatherization Assistance Program including technical assistance to help households and landlords manage the process. | Being Implemented
Expand workforce development programs such as the VT Training Program or the Department of Labor’s Workforce Education & Training Fund; cover costs for businesses to train in-house auditors/technicians. Pilot new programs in rural areas where workforce needed is greater. | Action not defined
Pathway 17: Change Vermont's land-use policies so current and future land development will be adaptive and resilient to climate change impacts
Strategy 17a: Increase investment in the infrastructure (sewer, water, stormwater, sidewalks, bike lanes, EV charging, broadband, energy supply) needed to support communities that are more resilient to climate disruptions, equitable, resource efficient, and protects the adaptive capacity of natural resources.
Invest in enhancing water sources in vulnerable communities to enhance resilience to long-term drought. | Advancing
Increase investment to municipalities for new and expanded water and wastewater facilities to support reductions in inflow and infiltration into wastewater collection systems. | Advancing
Monitor and update stormwater permitting process as needed to ensure green infrastructure is preferred in design considerations. | Being Implemented
Complete a Climate Readiness assessments of drinking water, stormwater, and wastewater infrastructure. (This is an EPA tool that looks at all climate impacts including, fires, droughts, flooding, etc.). | No Action Taken
Examine regionalization efforts and sharing of resources for all water utilities. | No Action Taken
Increase investment in stormwater and green infrastructure, including separating combined wastewater and storm water systems, to protect public health and water quality. | Being Implemented
Strategy 17b: Develop permanent private and public funding sources to floodproof, elevate and purchase commercial and residential properties, as well as conserve and restore ecosystem services upstream to protect our people, property, environment, and economy from flooding.
Fund ERAF for non-federal disasters in towns that have adopted floodplain and/or river corridor bylaws and to support the 25% non-federal match for buyouts and develop criteria for distribution when funding is limited. | No Action Taken
Establish a dedicated, comprehensive state level program with funding to strategically purchase or match funding for hazard-prone properties, easements to conserve river corridors, floodplains, forests, and wetlands to reduce overall flood risk and enhance flood storage statewide. | Advancing
Expand the eligibility criteria and increase funding for VHCB's conservation and buyout program, to address any flood-vulnerable structures. | No Action Taken
Pathway 18: Ensure that all people have access to safe, accessible, energy efficient, and affordable housing.
Strategy 18a: Update state and local land-use governance, regulations, practices, and investments to eliminate barriers to housing development.
Increase manufactured housing tax credits to replace older and inefficient manufactured homes. | Being Implemented
Expand pilot program to train a network of local builders in the design and building of small and mid-sized and accessory dwelling units (mother-in-law apartments) and fund homes starts within communities planning and investing in development-ready infrastructure, building development partnerships, and updating zoning bylaws to welcome new homes. | Being Implemented
Convene a statewide conversation on the Vermont Municipal and Regional Planning and Development Act’s (24 VSA, Chapter 117) provisions on land use and housing to outline amendments and strategies that will expand housing choice, opportunity, and improve community resilience. | Completed
Expand the existing program to relocate mobile home park homes and residents outside of flood vulnerable locations. | No Action Taken
Create a rental registry and inspection program to locate all of Vermont's rental housing and improve their quality and safety. | No Action Taken
Strategy 18b: Increase investments in the preservation and development of both private-market and nonprofit-owned affordable housing.
Continue to fund housing investments that leverage private initiative and funding to cost-effectively create housing units under models like the Re-Housing Recovery Program funding and the proposed Vermont Housing Investment Program. | Being Implemented
Create programs to assist prospective homebuyers to purchase and make improvements to homes that are energy inefficient and otherwise in need of immediate investment. | Being Implemented
Increase support for mission-driven, non-profit housing developers to maintain their ability to produce high-quality, energy- and location-efficient housing. | Being Implemented
Strategy 18c: Increase access to fair and affordable housing for Vermonters who are housing instable
Implement the recommendations of the Analysis of Impediments to Fair Housing. | Being Implemented
Increase funding for community-based homelessness prevention and rapid re-housing. | Advancing
Audit existing residential building codes to ensure that standards account for anticipated climate change impacts to Vermont, including but not limited to increased temperatures extremes and precipitation (combine into a single building code action) | No Action Taken

## Public Health
Existing Recommendations
Action | Status | Revise Action, Revise Strategy, Remove, Keep as is | Proposed Revised Language | Notes
Pathway 14: Increase capacity for climate resilience planning and implementation, and address inequities of under-resourced communities.
Strategy 14a: Provide tools and resources to help communities assess climate vulnerabilities and create climate resilience plans.
Strategy 14b: Establish permanent statewide funding and technical support for local and regional climate resilience planning and project implementation to enhance rural resilience to impacts of climate change.
Establish a state level individual assistance program to provide financial assistance to uninsured or underinsured households impacted by disasters not federally declared. Program should incorporate Community Action Agencies and supporting networks to ensure assistance is received expeditiously by those that need it most. | No Action Taken |  |  |  | Community & Public Health
Pathway 15: Proactively and strategically invest to enhance resilience in transportation, communications, water/wastewater, and energy infrastructure statewide.
Strategy 15a: Create a policy, planning and organizational foundation to support effective investments in infrastructure resilience.
Strategy 15b: Public, private, and nonprofit entities should be prepared to respond and recover quickly to disruptions caused by severe weather and other climate change threats.
Strategy 15c: Increase the resilience of critical infrastructure to severe weather and other climate change threats by reducing vulnerabilities of specific facilities.
Strategy 15d: Increase the resilience of critical infrastructure to severe weather and other climate change threats by improving system efficiency, reliability and redundancies.
Pathway 16: Support the reduction of municipal, school district, residential, university, and hospital fossil fuel use in rural areas through equitable best practices that address the unique challenges of rural communities. |  |  |  |  | Overlap with CSM so TBD
Pathway 17: Change Vermont's land-use policies so current and future land development will be adaptive and resilient to climate change impacts
Strategy 17a: Increase investment in the infrastructure (sewer, water, stormwater, sidewalks, bike lanes, EV charging, broadband, energy supply) needed to support communities that are more resilient to climate disruptions, equitable, resource efficient, and protects the adaptive capacity of natural resources.
Strategy 17b: Develop permanent private and public funding sources to floodproof, elevate and purchase commercial and residential properties, as well as conserve and restore ecosystem services upstream to protect our people, property, environment, and economy from flooding.
Pathway 18: Ensure that all people have access to safe, accessible, energy efficient, and affordable housing.
Strategy 18a: Update state and local land-use governance, regulations, practices, and investments to eliminate barriers to housing development.
Increase manufactured housing tax credits to replace older and inefficient manufactured homes. | Being Implemented |  |  |  | Public Health & Infrastructure
Expand pilot program to train a network of local builders in the design and building of small and mid-sized and accessory dwelling units (mother-in-law apartments) and fund homes starts within communities planning and investing in development-ready infrastructure, building development partnerships, and updating zoning bylaws to welcome new homes. | Being Implemented |  |  |  | Community & Infrastructure
Convene a statewide conversation on the Vermont Municipal and Regional Planning and Development Act’s (24 VSA, Chapter 117) provisions on land use and housing to outline amendments and strategies that will expand housing choice, opportunity, and improve community resilience. | Completed |  |  |  | Community
Expand the existing program to relocate mobile home park homes and residents outside of flood vulnerable locations. | No Action Taken |  |  |  | Community & Infrastructure
Create a rental registry and inspection program to locate all of Vermont's rental housing and improve their quality and safety. | No Action Taken |  |  |  | Public Health & Infrastructure
Strategy 18b: Increase investments in the preservation and development of both private-market and nonprofit-owned affordable housing.
Continue to fund housing investments that leverage private initiative and funding to cost-effectively create housing units under models like the Re-Housing Recovery Program funding and the proposed Vermont Housing Investment Program. | Being Implemented |  |  |  | Infrastructure
Create programs to assist prospective homebuyers to purchase and make improvements to homes that are energy inefficient and otherwise in need of immediate investment. | Being Implemented |  |  |  | Public Health & Infrastructure
Increase support for mission-driven, non-profit housing developers to maintain their ability to produce high-quality, energy- and location-efficient housing. | Being Implemented |  |  |  | Community & Infrastructure
Strategy 18c: Increase access to fair and affordable housing for Vermonters who are housing instable
Implement the recommendations of the Analysis of Impediments to Fair Housing. | Being Implemented |  |  |  | Public Health & Infrastructure
Increase funding for community-based homelessness prevention and rapid re-housing. | Advancing |  |  |  | Public Health & Infrastructure
Audit existing residential building codes to ensure that standards account for anticipated climate change impacts to Vermont, including but not limited to increased temperatures extremes and precipitation (combine into a single building code action) | No Action Taken |  |  |  | ?
New Recommendations
Action | Status | Revise Action, Revise Strategy, Remove, Keep as is | Proposed Revised Language | Notes
Pathway
Strategy:

## Public Health New
Public Health Recommendations |  |  |  |  | Prioritization Criteria
Action | Status | Revise Action, Revise Strategy, Remove, Keep as is | Proposed Language | Notes | Technical Feasability (yes/no) | Impact (High/Moderate/ Low) | Cost - Effectiveness (High/Medium/Low) | Co-Benefits (High/Medium/Low)
Pathway: Support equitable adaptation to the public health impacts of climate change
Strategy 19.a: Increase support for regional, municipal, and community partners to mitigate, prepare, and respond to climate impacts on health.
N/A | N/A | New | Explore and implement strategies to enhance local emergency preparedness, response, and recovery capacity (e.g., increase funding and expand authority of RPCs and/or county government; increase direct state funding, training, and technical assistance provided to municipalities). | RPCs or county governments would likely need additional funding, staffing, and authority to better support municipalities. State support could be bolstered by dedicating additional resources to VEM Regional Coordinators and/or VDH Local Health Office Emergency Preparedness Specialists. | yes | High | med | High | o
N/A | N/A | New | Provide funding and technical assistance to local partners to develop community resilience hubs that can serve as places for learning, collaboration, resource access, and refuge in response to climate-related hazards and other community needs. | Potential uses could include daytime relief or overnight sheltering from flooding, power outages, extreme temperatures, hazardous air quality, and other climate-related hazards. | yes | High | med | High | o
N/A | N/A | New | Provide funding and technical assistance to municipalities and local organizations to reduce health impacts of climate change for the disproportionately affected populations they serve, through preparedness, facility adaptation, and support for individuals and households. | Disproportionately affected populations include overburdened and underserved communities, unhoused individuals, older adults, children, people with health sensitivities, outdoor workers, and other environmental justice populations as defined in Vermont's Environmental Justice law. Supported strategies should include 1) emergency preparedness and response planning, 2) adapting facilities (including hospitals, residential care facilities, homeless shelters, places used for emergency shelter, and other facilities housing people with health vulnerabilities) to be more resilient to climate-related hazards including flooding, extreme temperatures, power outages, and hazardous air quality, and 3) outreach and other support for disproportionately affected populations needing extra assistance. | Yes | High | med | High | X
Strategy 19.b: Increase support for individuals and households to prepare and adapt to climate impacts on health
N/A | N/A | New | Review/improve existing tools and/or develop new tools to better identify and support Vermonters needing extra assistance during an emergency, including state systems such as the Citizens Assistance Registry for Emergencies and its integration with the Vermont 2-1-1 system, support for local systems managed by municipal and community partners, or other alternatives. |  | yes | high | high | high | X
N/A | N/A | New | Provide funding for resilience equipment, supplies, and services that help reduce the health impact of climate-related hazards for income-qualifying households needing extra assistance. | This would require new funding & programming. The intent is to provide financial support for resilience needs in a similar way to existing financial support for energy efficiency (e.g., through heat pump and EV rebates). Resilience equipment and strategies should address health risks related to flooding, power outages, extreme temperatures, hazardous air quality, humidity, vectorborne diseases, and other climate-related hazards, and should include trees and other vegetative shade, window treatments (shade, thermal barriers), efficient air conditioning (heat pumps), fans, air purifiers, mechanical ventilation (e.g. ERVs), water intrusion and moisture mitigation & management, backup power, window screens, private drinking water testing and treatment, etc. | yes | High | med | High | X
N/A | N/A | New | Increase funding for state-contracted community mental health services, to provide funded partners with more capacity to address anxiety, depression, distress, and trauma caused by climate change and climate-related disasters. |  | yes | High | med | High | X
|  | New | Action: Adopt a policy to prioritize state climate mitigation spending on actions that maximize public health, climate resilience, and health equity co-benefits, while minimizing the potential for co-harms. |  | yes | med | High | High
Strategy 19.c:Expand state capacity to plan, prepare, and respond to climate-related health hazards.
N/A | N/A | New | Action: Direct state agencies to collaborate across relevant agencies to develop, maintain, and exercise state response plans and mechanisms for addressing climate-related health hazards including flooding, extreme temperatures, power loss, hazardous air quality, and infectious diseases. |  | yes | med | high | med
N/A | N/A | New | Action: Fund increased state staff capacity and resources to better plan, prepare, and respond to climate-related health hazards, including increased support for regional, municipal, and community partners. |  | yes | High | med | high | X
Strategy 19.d: Improve tools and mechanisms for increasing awareness about climate impacts on health and potential adaptation strategies.
N/A | N/A | New | Routinely review and update publicly-available information about the highest priority climate-related health risks for Vermont. | VDH is already doing this, but it's important to continue. | yes | High | High | low
N/A | N/A | New | Communicate to the public, communities, and state partners about climate-related health risks and offer guidance about what individuals and communities can do to reduce their risks, with specific focus on disproportionately affected populations (including overburdened and underserved communities, unhoused individuals, older adults, children, people with health sensitivities, and outdoor workers). | VDH is already doing this, but this work could be expanded. | Yes | High | High | med
N/A | N/A | New | Direct state agencies to develop improved tools and approaches for communicating with community partners, with people in languages other than English, and with other underserved populations (including rural, unhoused, and isolated individuals). | VEM, ANR, and VDH are already working on this to some extent. | yes | High | High | High | X/o?

## Definitions
Action_Status | Action Status Definitions | Priority | Definitions
Action not defined |  | High | Administratively supported; capacity exists to implement (however implementation funds needed); high-impact (degree of impact for state agencies to determine)
No Action Taken | Lead Implementer or others have not taken any action | Medium | Not enough info to gain administrative support; Limited or unknown capacity; impact is limited or not defined
Advancing | Lead Implementer is in a planning or design phase | Low | Lack of administrative support; no capacity to implement, even with implementation funding(CPRG); low-impact
Being Implemented | Action is ongoing with resources allocated | Not Reviewed | Not reviewed
Completed | Lead implementer has completed work on the specific action
Action Modified - Advancing | Modified version of a CAP action is in a planning or design phase
Action Modified - Being Implemented | Modified version of a CAP action is ongoing with resources allocated
Action Modified - Completed | Modified version of a CAP action has been completed
Need more information | Information on progress not provided